## Summary
Intelligrator — User Story Backlog
Requester journey (MFT + API submission) and Approver journey (accept / reject)
Version 1.0 · 14 July 2026 · Boomi iPaaS, Boomi native MFT (Thru), Boomi API Management
Totals
Total stories | 49
Total story points | 242
Must have | 39
Should have | 9
Could have | 1
Must-have points | 204
Total acceptance criteria | 206
By epic
Epic | Name | Primary persona | Stories | Points | Must | Should | Could
E1 | Portal Access & Identity | P1 / P2 | 5 | 16 | 4 | 1 | 0
E2 | Request Initiation & Guidance | P1 | 3 | 16 | 3 | 0 | 0
E3 | MFT Request Submission | P1 | 10 | 52 | 10 | 0 | 0
E4 | API Request Submission | P1 | 7 | 39 | 6 | 1 | 0
E5 | Track, Amend & Withdraw | P1 | 6 | 23 | 3 | 3 | 0
E6 | Admin Access & Approval Queue | P2 | 4 | 26 | 4 | 0 | 0
E7 | Decision: Accept / Reject | P2 | 7 | 31 | 4 | 2 | 1
E8 | Provisioning on Approval | P2 / P3 | 3 | 21 | 3 | 0 | 0
E9 | Audit, Reporting & NFRs | All | 4 | 18 | 2 | 2 | 0
| TOTAL |  | 49 | 242 | 39 | 9 | 1
Legend / how to use
• Yellow-filled, blue-text cells on the Backlog and Acceptance Criteria sheets are yours to fill in: Sprint, Status, Owner, Notes, Test Ref, Pass/Fail.
• Every other cell is either source content or a formula. Do not overtype a formula — the Summary sheet recalculates from the Backlog sheet.
• Status on the Backlog sheet is a drop-down: Not started / In refinement / Ready / In progress / In test / Done / Deferred.
• Story IDs are stable and are the join key between the Backlog and Acceptance Criteria sheets. Do not renumber them.
• Example row: Sprint = "Sprint 1", Status = "Ready", Owner = "A. Patel", Notes = "Depends on IdP group config".
• Points are unmodified planning-poker estimates carried from refinement; they are inputs, not calculations.

## Backlog
Story ID | Epic | Epic Name | Persona | Title | User Story | Priority | Points | AC Count | Sprint | Status | Owner | Notes
ACC-01 | E1 | Portal Access & Identity | Standard User | Discover the portal and understand what it is for | As a Standard User, I want a landing page that explains what Intelligrator onboards and what it does not, so that I do not waste time submitting a request the portal cannot service. | Must | 3 | 4 |  | Not started
ACC-02 | E1 | Portal Access & Identity | Standard User | Sign in with departmental single sign-on | As a Standard User, I want to sign in using my existing departmental identity via SSO, so that I do not need another credential and my access reflects my organisational role. | Must | 5 | 4 |  | Not started
ACC-03 | E1 | Portal Access & Identity | Standard User | Role-based landing dashboard | As a Standard User, I want a dashboard on sign-in showing my requests and a clear call to action to raise a new one, so that I can pick up where I left off in one click. | Must | 3 | 4 |  | Not started
ACC-04 | E1 | Portal Access & Identity | Standard User | Organisation and service-line context | As a Standard User, I want my requests automatically associated with my organisation and service line, so that approval routing and ownership are correct without manual entry. | Must | 3 | 3 |  | Not started
ACC-05 | E1 | Portal Access & Identity | Standard User | Secure session handling and sign-out | As a Standard User, I want my session to expire on inactivity and to be able to sign out explicitly, so that an unattended machine cannot be used to submit or approve requests. | Should | 2 | 4 |  | Not started
REQ-01 | E2 | Request Initiation & Guidance | Standard User | Choose the request type: MFT or API | As a Standard User, I want to choose whether I am requesting a file transfer or an API, so that I am shown only the fields relevant to my interface. | Must | 3 | 4 |  | Not started
REQ-02 | E2 | Request Initiation & Guidance | Standard User | Guided pattern selection with anti-pattern detection | As a Standard User, I want the portal to ask me about my non-functional needs and recommend the right interaction style, so that I do not accidentally request an async workload disguised as a synchronous API. | Must | 8 | 4 |  | Not started
REQ-03 | E2 | Request Initiation & Guidance | Standard User | Save a draft and resume later | As a Standard User, I want to save a partially completed request and come back to it, so that I can go and find information I do not have to hand without losing my work. | Must | 5 | 4 |  | Not started
MFT-01 | E3 | MFT Request Submission | Standard User | Capture MFT interface identity and ownership | As a Standard User, I want to name my file transfer interface and record who owns it, so that it can be uniquely identified, supported and charged correctly for its whole life. | Must | 5 | 4 |  | Not started
MFT-02 | E3 | MFT Request Submission | Standard User | Define source and target endpoints and transfer direction | As a Standard User, I want to declare where the file comes from and where it goes, and by what protocol, so that the generic MFT engine can be configured without any bespoke build. | Must | 8 | 4 |  | Not started
MFT-03 | E3 | MFT Request Submission | Standard User | Specify file characteristics and volumetrics | As a Standard User, I want to describe the files themselves, so that the platform can validate what arrives and capacity-plan for it. | Must | 5 | 4 |  | Not started
MFT-04 | E3 | MFT Request Submission | Standard User | Specify the trigger: event-driven, polled or scheduled | As a Standard User, I want to declare how the transfer is initiated, so that the engine either watches, polls or schedules it correctly. | Must | 5 | 4 |  | Not started
MFT-05 | E3 | MFT Request Submission | Standard User | Declare security: keys, certificates, encryption and allow-listing | As a Standard User, I want to supply or request the credentials and encryption my transfer needs, so that the interface is secure by default and no secret is ever emailed. | Must | 8 | 5 |  | Not started
MFT-06 | E3 | MFT Request Submission | Standard User | Declare data classification and residency | As a Standard User, I want to classify the data in the files and state where it may reside, so that the approver can assess risk and the platform can route the transfer to a compliant region. | Must | 5 | 4 |  | Not started
MFT-07 | E3 | MFT Request Submission | Standard User | Configure error handling, retries and alert routing | As a Standard User, I want to say what should happen when a transfer fails and who should be told, so that failures are handled predictably and reach the right team. | Must | 5 | 4 |  | Not started
MFT-08 | E3 | MFT Request Submission | Standard User | Select environments and promotion path | As a Standard User, I want to request the interface in a specific environment and understand the path to production, so that expectations about go-live are clear from the outset. | Must | 3 | 4 |  | Not started
MFT-09 | E3 | MFT Request Submission | Standard User | Review the generated config row before submitting | As a Standard User, I want to see exactly what configuration my answers will produce, so that I can confirm it is right before it goes for approval — and so I can see that no bespoke build is being requested on my behalf. | Must | 5 | 4 |  | Not started
MFT-10 | E3 | MFT Request Submission | Standard User | Submit the MFT request for approval | As a Standard User, I want to submit my completed MFT request, so that it enters the approval queue and I get a reference I can quote. | Must | 3 | 5 |  | Not started
API-01 | E4 | API Request Submission | Standard User | Capture API identity, ownership and consumer intent | As a Standard User, I want to record what API I am publishing or consuming and who owns it, so that it can be governed, discovered and supported. | Must | 5 | 4 |  | Not started
API-02 | E4 | API Request Submission | Standard User | Provide the contract first — OpenAPI or AsyncAPI | As a Standard User, I want to upload or link my API contract as the primary artefact of the request, so that the design is agreed before anything is provisioned. | Must | 8 | 5 |  | Not started
API-03 | E4 | API Request Submission | Standard User | Declare the interaction style with NFR-driven justification | As a Standard User, I want to declare whether my API is synchronous request/response, asynchronous, or publish/subscribe, and justify it against NFRs, so that the platform is not asked to expose an unsuitable back-end behind a blocking call. | Must | 5 | 4 |  | Not started
API-04 | E4 | API Request Submission | Standard User | Define the authentication and authorisation model | As a Standard User, I want to declare how consumers of my API will authenticate, so that the correct gateway policy is applied and no unprotected endpoint is ever published. | Must | 8 | 5 |  | Not started
API-05 | E4 | API Request Submission | Standard User | Declare traffic profile, rate limits and service levels | As a Standard User, I want to declare my expected load and required service level, so that gateway throttling is set correctly and the platform can capacity-plan. | Must | 5 | 4 |  | Not started
API-06 | E4 | API Request Submission | Standard User | Select environment, routing and gateway policy set | As a Standard User, I want to declare the environment and back-end routing for my API, so that the gateway can be configured from my request without a bespoke build. | Should | 5 | 4 |  | Not started
API-07 | E4 | API Request Submission | Standard User | Review and submit the API request | As a Standard User, I want to review the full API request and submit it, so that it enters the approval queue with a reference I can quote. | Must | 3 | 4 |  | Not started
TRK-01 | E5 | Track, Amend & Withdraw | Standard User | Track the status of my requests | As a Standard User, I want to see where each of my requests is in the approval process, so that I do not have to chase anyone to find out. | Must | 5 | 4 |  | Not started
TRK-02 | E5 | Track, Amend & Withdraw | Standard User | Be notified when a decision or query is raised | As a Standard User, I want to be notified when my request is approved, rejected or queried, so that I can act without watching the portal. | Must | 3 | 4 |  | Not started
TRK-03 | E5 | Track, Amend & Withdraw | Standard User | Respond to a request for more information | As a Standard User, I want to answer an approver's query and resubmit, so that a query does not force me to start again. | Must | 5 | 4 |  | Not started
TRK-04 | E5 | Track, Amend & Withdraw | Standard User | Amend a rejected request and resubmit | As a Standard User, I want to clone a rejected request, fix the issue and resubmit, so that I retain the effort I already invested. | Should | 3 | 3 |  | Not started
TRK-05 | E5 | Track, Amend & Withdraw | Standard User | Withdraw a request | As a Standard User, I want to withdraw a request that is no longer needed, so that I do not consume approver time on work that has been cancelled. | Should | 2 | 3 |  | Not started
TRK-06 | E5 | Track, Amend & Withdraw | Standard User | Request a change or decommission of a live interface | As a Standard User, I want to change or retire an interface that is already live, so that the config store stays accurate and dead interfaces do not linger. | Should | 5 | 4 |  | Not started
ADM-01 | E6 | Admin Access & Approval Queue | MFT Admin | Sign in as an administrator with step-up authentication | As an MFT Admin, I want to sign in with my elevated role and complete a step-up authentication challenge, so that approval authority cannot be exercised from a merely-authenticated session. | Must | 5 | 5 |  | Not started
ADM-02 | E6 | Admin Access & Approval Queue | MFT Admin | Work an approval queue prioritised by risk and SLA | As an MFT Admin, I want a single queue of everything awaiting my decision, ordered so the urgent and risky surface first, so that I spend my attention where it matters. | Must | 8 | 5 |  | Not started
ADM-03 | E6 | Admin Access & Approval Queue | MFT Admin | Open a request and see the complete submission | As an MFT Admin, I want to see everything the requester submitted on one screen, so that I can make a decision without hunting through attachments or emailing for context. | Must | 5 | 5 |  | Not started
ADM-04 | E6 | Admin Access & Approval Queue | MFT Admin | See the automated pre-check results before deciding | As an MFT Admin, I want the platform to have already checked the mechanical things, so that my review is spent on judgement rather than on validation a machine could do. | Must | 8 | 5 |  | Not started
DEC-01 | E7 | Decision: Accept / Reject | MFT Admin | Approve a request | As an MFT Admin, I want to approve a request with a recorded rationale, so that the interface can be provisioned and the decision is defensible after the fact. | Must | 5 | 5 |  | Not started
DEC-02 | E7 | Decision: Accept / Reject | MFT Admin | Reject a request with a reason the requester can act on | As an MFT Admin, I want to reject a request with a structured reason, so that the requester understands precisely what to fix and does not simply resubmit the same thing. | Must | 5 | 5 |  | Not started
DEC-03 | E7 | Decision: Accept / Reject | MFT Admin | Return a request for more information | As an MFT Admin, I want to ask the requester a question without rejecting the request outright, so that a single missing detail does not cost the requester a full resubmission. | Must | 5 | 4 |  | Not started
DEC-04 | E7 | Decision: Accept / Reject | MFT Admin | Approve conditionally, with binding conditions | As an MFT Admin, I want to approve a request subject to stated conditions, so that a low-risk interface is not held up while a non-blocking issue is resolved. | Should | 5 | 4 |  | Not started
DEC-05 | E7 | Decision: Accept / Reject | MFT Admin | Reassign or delegate a request to another approver | As an MFT Admin, I want to hand a request to a colleague, so that absence or a specialist question does not stall the queue. | Should | 3 | 3 |  | Not started
DEC-06 | E7 | Decision: Accept / Reject | MFT Admin | Enforce segregation of duties | As an MFT Admin, I want the platform to make it impossible for anyone to approve their own request, so that the control is guaranteed by the system rather than by good behaviour. | Must | 3 | 4 |  | Not started
DEC-07 | E7 | Decision: Accept / Reject | MFT Admin | Fast-path approval for low-risk requests | As an MFT Admin, I want to approve a batch of requests that passed every pre-check and carry no risk flags, so that routine non-production work does not consume the same effort as a production change. | Could | 5 | 4 |  | Not started
PRV-01 | E8 | Provisioning on Approval | Platform Engineer | Approval writes a configuration row — not a new component | As a Platform Engineer, I want an approved request to become a row in the config store consumed by the existing generic engine, so that the estate does not accumulate one Boomi component per interface. | Must | 8 | 5 |  | Not started
PRV-02 | E8 | Provisioning on Approval | Standard User | Issue credentials securely on approval | As a Standard User, I want any keys or credentials my interface needs to be issued and delivered securely, so that no secret is ever sent by email or displayed in a page I might screenshot. | Must | 8 | 5 |  | Not started
PRV-03 | E8 | Provisioning on Approval | MFT Admin | See provisioning succeed or fail, and roll back cleanly | As an MFT Admin, I want to know whether the approval actually resulted in a working interface, so that an approved-but-broken interface does not sit undetected. | Must | 5 | 4 |  | Not started
AUD-01 | E9 | Audit, Reporting & NFRs | MFT Admin | Maintain an immutable audit trail | As an MFT Admin, I want every action on every request permanently recorded, so that I can demonstrate to an auditor exactly who approved what, when and on what basis. | Must | 5 | 5 |  | Not started
AUD-02 | E9 | Audit, Reporting & NFRs | MFT Admin | Report on throughput, SLA and rejection reasons | As an MFT Admin, I want to see how the onboarding service is actually performing, so that I can fix the causes of rejection rather than just processing the symptoms. | Should | 5 | 5 |  | Not started
NFR-01 | E9 | Audit, Reporting & NFRs | All | Meet accessibility standards | As any user, I want the portal to be usable with assistive technology, so that the service is available to every colleague and meets the department's legal obligation. | Must | 5 | 4 |  | Not started
NFR-02 | E9 | Audit, Reporting & NFRs | All | Meet performance and availability targets | As any user, I want the portal to be responsive and available, so that it is faster to self-serve than to raise a ticket — otherwise nobody will use it. | Should | 3 | 4 |  | Not started

## Acceptance Criteria
Story ID | Epic | Story Title | AC # | Acceptance Criterion (Given / When / Then) | Test Ref | Pass/Fail
ACC-01 | E1 | Discover the portal and understand what it is for | 1 | Given I am an unauthenticated visitor, when I open the portal URL, then I see a landing page stating that Intelligrator onboards Managed File Transfer interfaces and APIs.
ACC-01 | E1 | Discover the portal and understand what it is for | 2 | And I see an explicit "not in scope" statement (no runtime data flows through the portal; no bespoke Boomi process build requests).
ACC-01 | E1 | Discover the portal and understand what it is for | 3 | And I see a single, prominent "Sign in" action.
ACC-01 | E1 | Discover the portal and understand what it is for | 4 | And I see links to the Integration Pattern Catalogue so I can self-assess which pattern applies before signing in.
ACC-02 | E1 | Sign in with departmental single sign-on | 1 | Given I hold a valid departmental identity, when I select "Sign in", then I am redirected to the corporate IdP (OIDC/SAML) and returned authenticated.
ACC-02 | E1 | Sign in with departmental single sign-on | 2 | Given authentication succeeds, when I land in the portal, then my display name, email and organisational unit are populated from IdP claims without me typing them.
ACC-02 | E1 | Sign in with departmental single sign-on | 3 | Given my IdP group entitles me only to the requester role, when I land, then no administrative navigation is rendered anywhere in the UI (not merely hidden by CSS).
ACC-02 | E1 | Sign in with departmental single sign-on | 4 | Given authentication fails, when I am returned, then I see a clear, non-technical error and a route to service support.
ACC-03 | E1 | Role-based landing dashboard | 1 | Given I sign in as a requester, when the dashboard loads, then I see counts for Draft, Submitted, Awaiting Info, Approved and Rejected.
ACC-03 | E1 | Role-based landing dashboard | 2 | And I see a primary "New request" button.
ACC-03 | E1 | Role-based landing dashboard | 3 | And I see my five most recently updated requests with status and last-updated timestamp.
ACC-03 | E1 | Role-based landing dashboard | 4 | Given I have no requests, when the dashboard loads, then I see an empty state that explains the next step rather than a blank panel.
ACC-04 | E1 | Organisation and service-line context | 1 | Given my IdP claims include an organisational unit, when I create a request, then the owning organisation is pre-populated and read-only.
ACC-04 | E1 | Organisation and service-line context | 2 | Given I belong to more than one service line, when I create a request, then I am asked to select which one this request belongs to.
ACC-04 | E1 | Organisation and service-line context | 3 | Given the service line drives the approver group, when I submit, then the request is routed to that group's queue.
ACC-05 | E1 | Secure session handling and sign-out | 1 | Given I have been inactive for the configured idle timeout, when the timeout elapses, then my session is terminated and I am returned to the landing page.
ACC-05 | E1 | Secure session handling and sign-out | 2 | Given I am two minutes from timeout, when the warning threshold is reached, then I am prompted and offered the option to extend.
ACC-05 | E1 | Secure session handling and sign-out | 3 | Given I have unsaved form input, when a timeout occurs, then that input is preserved as a draft rather than lost.
ACC-05 | E1 | Secure session handling and sign-out | 4 | Given I select "Sign out", when the action completes, then the session token is invalidated server-side, not just cleared client-side.
REQ-01 | E2 | Choose the request type: MFT or API | 1 | Given I select "New request", when the type picker loads, then I am offered "Managed File Transfer (MFT)" and "API" with a one-line description of each.
REQ-01 | E2 | Choose the request type: MFT or API | 2 | And each option shows the governing catalogue pattern reference (for example P-116 for MFT) so the choice is anchored to the standard.
REQ-01 | E2 | Choose the request type: MFT or API | 3 | Given I choose a type, when I continue, then the correct submission form is loaded and the type is fixed for the life of the request.
REQ-01 | E2 | Choose the request type: MFT or API | 4 | Given I am unsure, when I select "Help me choose", then I am taken to the guided selection wizard (REQ-02).
REQ-02 | E2 | Guided pattern selection with anti-pattern detection | 1 | Given I enter the wizard, when it runs, then it asks about response-time budget, back-end availability, expected volume, payload size and reliability/delivery guarantee — not about the number of consumers.
REQ-02 | E2 | Guided pattern selection with anti-pattern detection | 2 | Given my back-end response time exceeds the synchronous budget or my payload exceeds the size threshold, when the wizard evaluates my answers, then it flags the synchronous option as an anti-pattern and recommends an asynchronous or file-based pattern with the reason stated in plain English.
REQ-02 | E2 | Guided pattern selection with anti-pattern detection | 3 | Given my answers indicate a bulk, scheduled or large-payload movement, when the wizard evaluates, then it recommends MFT and offers to start an MFT request pre-populated with my answers.
REQ-02 | E2 | Guided pattern selection with anti-pattern detection | 4 | Given the wizard makes a recommendation, when I disagree, then I may override it, but the override and my stated justification are recorded on the request and surfaced to the approver.
REQ-03 | E2 | Save a draft and resume later | 1 | Given I am part-way through a form, when I select "Save draft", then the request is persisted with status Draft and no validation is enforced.
REQ-03 | E2 | Save a draft and resume later | 2 | And drafts auto-save at a defined interval without me taking any action.
REQ-03 | E2 | Save a draft and resume later | 3 | Given I return to a draft, when I open it, then every previously entered value is restored and I resume at the section I left.
REQ-03 | E2 | Save a draft and resume later | 4 | Given a draft has not been touched for the configured retention period, when the retention job runs, then I am notified before it is archived.
MFT-01 | E3 | Capture MFT interface identity and ownership | 1 | Given I start an MFT request, when I complete the identity section, then I must supply an interface name, business purpose, owning service, technical contact and business owner.
MFT-01 | E3 | Capture MFT interface identity and ownership | 2 | Given the naming standard is enforced by the platform, when I enter a name that does not conform, then I am shown the required convention inline and cannot proceed until it conforms.
MFT-01 | E3 | Capture MFT interface identity and ownership | 3 | Given an interface with the same name already exists, when I attempt to proceed, then I am warned of the collision and offered a link to the existing interface.
MFT-01 | E3 | Capture MFT interface identity and ownership | 4 | Given all mandatory identity fields are complete, when I continue, then the section is marked complete in the progress indicator.
MFT-02 | E3 | Define source and target endpoints and transfer direction | 1 | Given I reach the endpoints section, when it loads, then I declare direction (inbound to the department, outbound to a partner, or internal) and select a protocol from the supported set (SFTP, AS2, HTTPS, FTPS).
MFT-02 | E3 | Define source and target endpoints and transfer direction | 2 | Given I select a protocol, when the form updates, then only the connection fields valid for that protocol are shown (for example, host/port/path/known-host key for SFTP; AS2 identifier and MDN settings for AS2).
MFT-02 | E3 | Define source and target endpoints and transfer direction | 3 | Given the platform distinguishes Accelerated File Transfer from standard File Streaming, when I declare a payload size above the AFT threshold or a cross-region route, then the portal recommends AFT and explains why.
MFT-02 | E3 | Define source and target endpoints and transfer direction | 4 | Given I complete the endpoint definition, when I continue, then the values map to named columns in the MFT config schema — no free-text blob is created.
MFT-03 | E3 | Specify file characteristics and volumetrics | 1 | Given I reach the file section, when I complete it, then I supply the filename pattern (glob or regex), file format, expected average and peak file size, and expected files per day and per peak hour.
MFT-03 | E3 | Specify file characteristics and volumetrics | 2 | Given I enter a filename pattern, when I select "Test pattern", then I can paste a sample filename and immediately see whether it matches.
MFT-03 | E3 | Specify file characteristics and volumetrics | 3 | Given my declared peak volumetrics exceed the platform capacity threshold, when I continue, then the request is automatically flagged for capacity review by the approver.
MFT-03 | E3 | Specify file characteristics and volumetrics | 4 | Given files must be archived or purged after transfer, when I complete the section, then I declare the retention period and post-transfer action (archive, delete, leave in place).
MFT-04 | E3 | Specify the trigger: event-driven, polled or scheduled | 1 | Given I reach the trigger section, when it loads, then I choose between event/arrival-driven, polled at an interval, or scheduled on a cron expression.
MFT-04 | E3 | Specify the trigger: event-driven, polled or scheduled | 2 | Given I choose polled, when I set the interval, then the portal enforces the minimum permitted polling interval and explains the reason for the floor.
MFT-04 | E3 | Specify the trigger: event-driven, polled or scheduled | 3 | Given I choose scheduled, when I enter a cron expression, then the portal shows the next five run times in plain English so I can confirm my intent.
MFT-04 | E3 | Specify the trigger: event-driven, polled or scheduled | 4 | Given the transfer has a business deadline, when I complete the section, then I declare the "must complete by" time so that SLA breach alerting can be configured.
MFT-05 | E3 | Declare security: keys, certificates, encryption and allow-listing | 1 | Given I reach the security section, when it loads, then I declare authentication method (SSH key, certificate, mutual TLS, username/password where permitted) for each endpoint.
MFT-05 | E3 | Declare security: keys, certificates, encryption and allow-listing | 2 | Given I hold a public key or certificate, when I upload it, then the portal validates its format, algorithm strength and expiry date and rejects a weak or expired credential with a clear reason.
MFT-05 | E3 | Declare security: keys, certificates, encryption and allow-listing | 3 | Given I do not hold a key, when I select "Request platform-generated key", then the request is marked for key issuance on approval and no secret is ever entered into a free-text field.
MFT-05 | E3 | Declare security: keys, certificates, encryption and allow-listing | 4 | Given payload encryption is required, when I complete the section, then I declare whether PGP encryption is applied and supply or request the relevant key.
MFT-05 | E3 | Declare security: keys, certificates, encryption and allow-listing | 5 | Given the platform enforces network controls, when I complete the section, then I supply the source IP ranges to be allow-listed.
MFT-06 | E3 | Declare data classification and residency | 1 | Given I reach the data section, when it loads, then I select a data classification from the departmental scheme and declare whether the payload contains personal data.
MFT-06 | E3 | Declare data classification and residency | 2 | Given I declare personal data, when I continue, then I must supply the lawful basis and the retention period, and the request is automatically flagged for enhanced review.
MFT-06 | E3 | Declare data classification and residency | 3 | Given I declare a residency constraint, when I continue, then the portal restricts the selectable target regions to those that satisfy the constraint.
MFT-06 | E3 | Declare data classification and residency | 4 | Given the classification exceeds the threshold for the selected protocol, when I attempt to continue, then I am blocked with an explanation of the required protocol or additional control.
MFT-07 | E3 | Configure error handling, retries and alert routing | 1 | Given I reach the resilience section, when I complete it, then I declare the retry count, retry interval and back-off strategy from the permitted options.
MFT-07 | E3 | Configure error handling, retries and alert routing | 2 | Given retries are exhausted, when I complete the section, then I declare the failure action (quarantine, alert only, alert and page).
MFT-07 | E3 | Configure error handling, retries and alert routing | 3 | Given an alert must reach a team, when I complete the section, then I supply an alert distribution address and, where paging is selected, an on-call rota reference.
MFT-07 | E3 | Configure error handling, retries and alert routing | 4 | Given the alert address does not resolve, when I attempt to submit, then validation fails with a clear message.
MFT-08 | E3 | Select environments and promotion path | 1 | Given I reach the environment section, when it loads, then I select the target environment (Development, Test, Pre-production, Production).
MFT-08 | E3 | Select environments and promotion path | 2 | Given I select Production, when I continue, then the portal shows the prerequisite environments that must already hold an approved, tested instance of this interface.
MFT-08 | E3 | Select environments and promotion path | 3 | Given a prerequisite is not met, when I attempt to submit for Production, then submission is blocked with a link to raise the prerequisite request.
MFT-08 | E3 | Select environments and promotion path | 4 | Given the same interface is promoted between environments, when I raise the promotion request, then all previously supplied values are carried forward and only environment-specific values (hosts, keys, IPs) are re-entered.
MFT-09 | E3 | Review the generated config row before submitting | 1 | Given every mandatory section is complete, when I reach the review step, then I see a read-only, human-readable rendering of the full config row that would be created.
MFT-09 | E3 | Review the generated config row before submitting | 2 | And I see a statement confirming that approval creates a configuration entry consumed by the shared MFT engine process, and does not create a new Boomi component.
MFT-09 | E3 | Review the generated config row before submitting | 3 | Given I spot an error, when I select the edit link beside any section, then I return to that section with my values intact and can return directly to review.
MFT-09 | E3 | Review the generated config row before submitting | 4 | Given a mandatory field is missing, when I reach review, then the incomplete sections are listed and the submit action is disabled.
MFT-10 | E3 | Submit the MFT request for approval | 1 | Given the request passes all validation, when I select "Submit", then the status changes from Draft to Submitted and the request becomes read-only to me.
MFT-10 | E3 | Submit the MFT request for approval | 2 | And a unique, human-quotable request reference is generated and displayed.
MFT-10 | E3 | Submit the MFT request for approval | 3 | And a confirmation is sent to me and to the nominated business owner.
MFT-10 | E3 | Submit the MFT request for approval | 4 | And the request appears in the approval queue of the approver group derived from my service line.
MFT-10 | E3 | Submit the MFT request for approval | 5 | Given submission fails for a technical reason, when the error occurs, then my request is retained as a Draft with all data intact and I am told plainly what to do next.
API-01 | E4 | Capture API identity, ownership and consumer intent | 1 | Given I start an API request, when I complete the identity section, then I declare whether I am publishing an API or requesting access to an existing one.
API-01 | E4 | Capture API identity, ownership and consumer intent | 2 | And I supply API name, business purpose, owning service, technical contact and business owner.
API-01 | E4 | Capture API identity, ownership and consumer intent | 3 | Given I am requesting access to an existing API, when I search the catalogue, then I can select the published API and my request is linked to it rather than duplicating its definition.
API-01 | E4 | Capture API identity, ownership and consumer intent | 4 | Given the naming standard is enforced, when I enter a non-conforming name, then I am blocked inline with the required convention shown.
API-02 | E4 | Provide the contract first — OpenAPI or AsyncAPI | 1 | Given I am publishing a synchronous API, when I reach the contract step, then I must supply an OpenAPI (3.x) document by upload or by URL.
API-02 | E4 | Provide the contract first — OpenAPI or AsyncAPI | 2 | Given I am publishing an event-driven or asynchronous interface, when I reach the contract step, then I must supply an AsyncAPI document instead.
API-02 | E4 | Provide the contract first — OpenAPI or AsyncAPI | 3 | Given I supply a contract, when it is received, then it is linted against the departmental API standards ruleset and every error and warning is displayed against the offending line.
API-02 | E4 | Provide the contract first — OpenAPI or AsyncAPI | 4 | Given the contract has linting errors of severity "error", when I attempt to submit, then submission is blocked until they are resolved.
API-02 | E4 | Provide the contract first — OpenAPI or AsyncAPI | 5 | Given I have no contract yet, when I reach this step, then I can download a conforming starter template rather than being left stuck.
API-03 | E4 | Declare the interaction style with NFR-driven justification | 1 | Given I reach the interaction step, when it loads, then I select from synchronous request/response, asynchronous (request/callback or polling), or publish/subscribe.
API-03 | E4 | Declare the interaction style with NFR-driven justification | 2 | And I supply the back-end response-time profile (p50, p95, p99), the back-end availability target, and the delivery guarantee required (at-most-once, at-least-once, exactly-once).
API-03 | E4 | Declare the interaction style with NFR-driven justification | 3 | Given my declared p99 exceeds the synchronous threshold, when I nonetheless select synchronous, then the anti-pattern is flagged, I must record a justification, and the flag is carried through to the approver.
API-03 | E4 | Declare the interaction style with NFR-driven justification | 4 | Given I select publish/subscribe, when I continue, then I declare the topic, the event schema reference and the expected subscriber growth.
API-04 | E4 | Define the authentication and authorisation model | 1 | Given I reach the security step, when it loads, then I select an authorisation model from the permitted set (OAuth 2.0 client credentials, OAuth 2.0 authorization code, mutual TLS, API key where permitted).
API-04 | E4 | Define the authentication and authorisation model | 2 | Given the platform forbids unauthenticated APIs, when no model is selected, then I cannot proceed.
API-04 | E4 | Define the authentication and authorisation model | 3 | Given I select OAuth 2.0, when I continue, then I declare the required scopes and the mapping of each scope to each operation in the contract.
API-04 | E4 | Define the authentication and authorisation model | 4 | Given I select mutual TLS, when I continue, then I upload or request the client certificate and the portal validates its algorithm strength and expiry.
API-04 | E4 | Define the authentication and authorisation model | 5 | Given credentials must be issued, when the request is approved, then they are issued by the platform and delivered by a secure one-time mechanism — never rendered in the portal UI or in an email body.
API-05 | E4 | Declare traffic profile, rate limits and service levels | 1 | Given I reach the traffic step, when I complete it, then I declare expected average TPS, peak TPS, peak window, average and maximum payload size, and required availability SLO.
API-05 | E4 | Declare traffic profile, rate limits and service levels | 2 | Given I declare a peak TPS above the standard tier, when I continue, then the request is automatically flagged for capacity review.
API-05 | E4 | Declare traffic profile, rate limits and service levels | 3 | Given rate limiting is mandatory, when I complete the step, then a default rate limit and burst allowance are proposed and I may request a different value with a justification.
API-05 | E4 | Declare traffic profile, rate limits and service levels | 4 | Given I request an availability SLO above the platform standard, when I continue, then I am shown the cost and architectural implication before I can proceed.
API-06 | E4 | Select environment, routing and gateway policy set | 1 | Given I reach the routing step, when I complete it, then I supply the back-end base URL per environment and the public-facing base path.
API-06 | E4 | Select environment, routing and gateway policy set | 2 | Given the base path collides with an existing published API, when I attempt to continue, then I am blocked and shown the conflicting API.
API-06 | E4 | Select environment, routing and gateway policy set | 3 | Given policy sets are standardised, when I complete the step, then I select from named, pre-approved gateway policy bundles (for example: standard, high-security, partner-facing) rather than composing policies myself.
API-06 | E4 | Select environment, routing and gateway policy set | 4 | Given I need a policy that no bundle provides, when I select "Request non-standard policy", then the request is routed for enhanced review with my justification attached.
API-07 | E4 | Review and submit the API request | 1 | Given every mandatory section is complete and the contract lints clean, when I reach review, then I see the full request including the resolved contract summary (operations, schemas, scopes).
API-07 | E4 | Review and submit the API request | 2 | And I see a statement confirming that approval creates gateway configuration from my declared values and does not create a bespoke integration component.
API-07 | E4 | Review and submit the API request | 3 | Given I submit, when submission succeeds, then the status changes to Submitted, a unique reference is generated, confirmations are sent, and the request enters the correct approval queue.
API-07 | E4 | Review and submit the API request | 4 | Given any anti-pattern flag or non-standard request is present, when the request enters the queue, then it is visibly badged as requiring enhanced review.
TRK-01 | E5 | Track the status of my requests | 1 | Given I open "My requests", when the list loads, then each request shows its reference, type, environment, current status, current owner and the age in working days.
TRK-01 | E5 | Track the status of my requests | 2 | Given I open a request, when the detail loads, then I see a full timeline of every state transition with actor and timestamp.
TRK-01 | E5 | Track the status of my requests | 3 | Given a request is awaiting approval, when I view it, then I see the target SLA date for the decision.
TRK-01 | E5 | Track the status of my requests | 4 | Given I want to find one request among many, when I use the filters, then I can filter by type, status, environment and date range.
TRK-02 | E5 | Be notified when a decision or query is raised | 1 | Given my request changes status, when the transition is committed, then I receive a notification containing the reference, the new status and the reason where one was given.
TRK-02 | E5 | Be notified when a decision or query is raised | 2 | And the notification contains a deep link to the request in the portal.
TRK-02 | E5 | Be notified when a decision or query is raised | 3 | And the notification never contains a secret, key or credential.
TRK-02 | E5 | Be notified when a decision or query is raised | 4 | Given the business owner is nominated on the request, when a terminal decision is made, then they are copied.
TRK-03 | E5 | Respond to a request for more information | 1 | Given the approver has set my request to "Awaiting Information", when I open it, then it becomes editable again and their question is displayed prominently against the section it concerns.
TRK-03 | E5 | Respond to a request for more information | 2 | Given I have answered, when I resubmit, then the request returns to the same approver (not to the back of a generic queue) with my answer attached to the thread.
TRK-03 | E5 | Respond to a request for more information | 3 | Given the request is Awaiting Information, when the SLA clock is evaluated, then the time spent waiting on me is excluded from the approver's SLA.
TRK-03 | E5 | Respond to a request for more information | 4 | Given I do not respond within the configured period, when the period elapses, then I am reminded, and after a second period the request is auto-withdrawn with notification.
TRK-04 | E5 | Amend a rejected request and resubmit | 1 | Given my request was rejected, when I select "Amend and resubmit", then a new request is created pre-populated with every value from the rejected one.
TRK-04 | E5 | Amend a rejected request and resubmit | 2 | And the new request retains a link to its predecessor and to the rejection reason.
TRK-04 | E5 | Amend a rejected request and resubmit | 3 | Given I resubmit, when the approver opens it, then they see a field-level difference against the rejected version so they can review only what changed.
TRK-05 | E5 | Withdraw a request | 1 | Given my request is in Draft or Submitted, when I select "Withdraw" and confirm, then its status becomes Withdrawn and it is removed from the approval queue.
TRK-05 | E5 | Withdraw a request | 2 | Given a request has been approved, when I view it, then "Withdraw" is not offered; I must instead raise a decommission request (TRK-06).
TRK-05 | E5 | Withdraw a request | 3 | And the withdrawal, with actor and timestamp, is written to the audit trail.
TRK-06 | E5 | Request a change or decommission of a live interface | 1 | Given an interface of mine is live, when I select "Request change", then a new request is opened pre-populated with the current live configuration.
TRK-06 | E5 | Request a change or decommission of a live interface | 2 | And the approver sees a field-level difference between the live config and the proposed config.
TRK-06 | E5 | Request a change or decommission of a live interface | 3 | Given I select "Request decommission", when the request is approved, then the config row is disabled (not deleted) and retained for the audit retention period.
TRK-06 | E5 | Request a change or decommission of a live interface | 4 | Given the interface has been inactive for the configured dormancy period, when the dormancy job runs, then I am prompted to confirm whether it is still required.
ADM-01 | E6 | Sign in as an administrator with step-up authentication | 1 | Given my IdP group grants the approver role, when I sign in, then the administrative navigation and approval queue are available to me.
ADM-01 | E6 | Sign in as an administrator with step-up authentication | 2 | Given I attempt a decision action (approve, reject, conditionally approve), when the action is invoked, then I am challenged for multi-factor step-up authentication before the decision is committed.
ADM-01 | E6 | Sign in as an administrator with step-up authentication | 3 | Given I fail the step-up challenge, when the decision is attempted, then no state change occurs and the failed attempt is written to the audit trail.
ADM-01 | E6 | Sign in as an administrator with step-up authentication | 4 | Given I do not hold the approver role, when I attempt to reach an administrative URL directly, then the server rejects the request — access is enforced at the API, not only in the UI.
ADM-01 | E6 | Sign in as an administrator with step-up authentication | 5 | Given administrative sessions carry higher risk, when I am idle, then a shorter idle timeout applies to me than to a standard user.
ADM-02 | E6 | Work an approval queue prioritised by risk and SLA | 1 | Given I open the approval queue, when it loads, then I see every request awaiting decision in my approver group with reference, type (MFT/API), requester, service line, environment, age in working days and SLA status.
ADM-02 | E6 | Work an approval queue prioritised by risk and SLA | 2 | And requests are badged where they carry an anti-pattern flag, an enhanced-review flag (personal data, non-standard policy, capacity), or a Production target.
ADM-02 | E6 | Work an approval queue prioritised by risk and SLA | 3 | And I can sort and filter by any of those attributes.
ADM-02 | E6 | Work an approval queue prioritised by risk and SLA | 4 | Given a request is approaching or has breached its decision SLA, when the queue renders, then it is visually distinguished.
ADM-02 | E6 | Work an approval queue prioritised by risk and SLA | 5 | Given the queue is empty, when it loads, then I see an explicit empty state rather than an ambiguous blank list.
ADM-03 | E6 | Open a request and see the complete submission | 1 | Given I open a request from the queue, when the detail loads, then every submitted section is rendered read-only in a single scrollable view with a section index.
ADM-03 | E6 | Open a request and see the complete submission | 2 | And for an MFT request I see the exact config row that would be written on approval.
ADM-03 | E6 | Open a request and see the complete submission | 3 | And for an API request I see the parsed contract summary — operations, schemas, scopes, and the linting result.
ADM-03 | E6 | Open a request and see the complete submission | 4 | Given the request is an amendment or a change to a live interface, when I open it, then I see a field-level difference highlighting only what changed.
ADM-03 | E6 | Open a request and see the complete submission | 5 | Given I need to see the history, when I open the timeline, then every prior state transition, comment and prior decision on the lineage is visible.
ADM-04 | E6 | See the automated pre-check results before deciding | 1 | Given a request enters the queue, when I open it, then a pre-check panel shows a pass/warn/fail result for each automated check.
ADM-04 | E6 | See the automated pre-check results before deciding | 2 | And the checks include at minimum: naming-standard conformance, duplicate/collision detection, credential strength and expiry, contract linting (API), data-classification-versus-protocol compatibility, capacity threshold, IP allow-list validity, and anti-pattern flags.
ADM-04 | E6 | See the automated pre-check results before deciding | 3 | Given any check has failed, when I view the panel, then the failure is stated in one line with a link to the offending field.
ADM-04 | E6 | See the automated pre-check results before deciding | 4 | Given every check has passed and the request carries no enhanced-review flag, when I view the request, then it is eligible for the low-risk fast path (DEC-07).
ADM-04 | E6 | See the automated pre-check results before deciding | 5 | Given a pre-check fails, when I attempt to approve, then I am not blocked, but I must record an explicit override justification which is retained in the audit trail.
DEC-01 | E7 | Approve a request | 1 | Given I am reviewing a request, when I select "Approve", then I am required to complete step-up authentication (ADM-01).
DEC-01 | E7 | Approve a request | 2 | And I may record an approval rationale, which is mandatory where any pre-check warned or failed, or where an anti-pattern flag is present.
DEC-01 | E7 | Approve a request | 3 | Given I confirm, when the decision commits, then the status becomes Approved, the request becomes immutable, and provisioning is triggered (PRV-01).
DEC-01 | E7 | Approve a request | 4 | And the requester and the business owner are notified.
DEC-01 | E7 | Approve a request | 5 | And the decision, the actor, the timestamp, the rationale and the state of every pre-check at the moment of decision are written to the immutable audit trail.
DEC-02 | E7 | Reject a request with a reason the requester can act on | 1 | Given I am reviewing a request, when I select "Reject", then I must choose at least one reason code from a governed list (for example: fails security policy, fails naming standard, unsuitable pattern, incomplete information, duplicate interface, capacity not available, data classification not permitted).
DEC-02 | E7 | Reject a request with a reason the requester can act on | 2 | And I must supply free-text detail; a reason code alone is not sufficient.
DEC-02 | E7 | Reject a request with a reason the requester can act on | 3 | And I may attach the rejection to one or more specific fields so the requester sees it in context.
DEC-02 | E7 | Reject a request with a reason the requester can act on | 4 | Given I confirm after step-up authentication, when the decision commits, then the status becomes Rejected, the requester and business owner are notified with the reason, and no provisioning occurs.
DEC-02 | E7 | Reject a request with a reason the requester can act on | 5 | Given the request is rejected, when the requester views it, then "Amend and resubmit" is offered (TRK-04).
DEC-03 | E7 | Return a request for more information | 1 | Given I am reviewing a request, when I select "Request information", then I must supply a question and may anchor it to one or more specific fields.
DEC-03 | E7 | Return a request for more information | 2 | Given I confirm, when the action commits, then the status becomes Awaiting Information, the request becomes editable by the requester, and it leaves my active queue.
DEC-03 | E7 | Return a request for more information | 3 | And my decision SLA clock is paused for the duration the request is with the requester.
DEC-03 | E7 | Return a request for more information | 4 | Given the requester responds, when they resubmit, then the request returns to me specifically, with their answer threaded against my question.
DEC-04 | E7 | Approve conditionally, with binding conditions | 1 | Given I am reviewing a request, when I select "Approve with conditions", then I must state each condition and a due date for it.
DEC-04 | E7 | Approve conditionally, with binding conditions | 2 | Given I confirm, when the decision commits, then provisioning proceeds, and the interface is flagged as conditionally approved in the config store.
DEC-04 | E7 | Approve conditionally, with binding conditions | 3 | Given a condition passes its due date unmet, when the condition-monitoring job runs, then the requester and I are alerted and the interface is escalated for review.
DEC-04 | E7 | Approve conditionally, with binding conditions | 4 | Given all conditions are marked met, when the last one is closed, then the conditional flag is cleared and the audit trail records who closed it.
DEC-05 | E7 | Reassign or delegate a request to another approver | 1 | Given I hold a request, when I select "Reassign", then I can select another approver within an eligible approver group and must supply a reason.
DEC-05 | E7 | Reassign or delegate a request to another approver | 2 | Given I reassign, when the action commits, then the request moves to their queue, the SLA clock continues unbroken, and the requester sees the new owner.
DEC-05 | E7 | Reassign or delegate a request to another approver | 3 | Given I will be absent, when I set a delegation period, then requests routed to me during that period are automatically routed to my nominated delegate.
DEC-06 | E7 | Enforce segregation of duties | 1 | Given I raised a request and I also hold the approver role, when that request reaches the queue, then it is not presented to me and the decision actions are not available to me on it.
DEC-06 | E7 | Enforce segregation of duties | 2 | And the rule is enforced server-side: a direct API call to approve my own request is rejected.
DEC-06 | E7 | Enforce segregation of duties | 3 | Given I am the only approver in the group, when I raise a request, then it is automatically routed to the escalation approver group rather than being blocked indefinitely.
DEC-06 | E7 | Enforce segregation of duties | 4 | Given any attempt to bypass the rule occurs, when it is rejected, then the attempt is written to the audit trail.
DEC-07 | E7 | Fast-path approval for low-risk requests | 1 | Given multiple requests have passed every automated pre-check, carry no enhanced-review flag and target a non-production environment, when I open the fast path, then I may select and approve them together.
DEC-07 | E7 | Fast-path approval for low-risk requests | 2 | Given I fast-path approve, when the decision commits, then step-up authentication is still required once for the batch, and each request receives its own individual audit entry.
DEC-07 | E7 | Fast-path approval for low-risk requests | 3 | Given any request in my selection is not fast-path eligible, when I attempt to include it, then it is excluded from the batch with the reason shown.
DEC-07 | E7 | Fast-path approval for low-risk requests | 4 | Given a request targets Production, when I attempt to fast-path it, then it is never eligible, regardless of pre-check results.
PRV-01 | E8 | Approval writes a configuration row — not a new component | 1 | Given a request is approved, when provisioning runs, then a single configuration record is written to the MFT config store (or the gateway policy store, for an API) keyed by the request reference.
PRV-01 | E8 | Approval writes a configuration row — not a new component | 2 | And no new Boomi process, connection or component is created for that interface.
PRV-01 | E8 | Approval writes a configuration row — not a new component | 3 | And the generic engine picks up the new configuration without redeployment.
PRV-01 | E8 | Approval writes a configuration row — not a new component | 4 | Given the config schema does not have a column for something a requester needs, when that gap is identified, then it is handled by a schema extension, never by a bespoke per-interface process.
PRV-01 | E8 | Approval writes a configuration row — not a new component | 5 | Given provisioning completes, when I inspect the config store, then the row is traceable to the approved request, the approver and the timestamp.
PRV-02 | E8 | Issue credentials securely on approval | 1 | Given my approved request asked for platform-generated credentials, when provisioning runs, then they are generated in the secrets store and never written to the portal database in plaintext.
PRV-02 | E8 | Issue credentials securely on approval | 2 | And I am notified that credentials are ready via a link that requires me to re-authenticate.
PRV-02 | E8 | Issue credentials securely on approval | 3 | And the secret is revealed once, is time-limited, and cannot be retrieved a second time through the portal.
PRV-02 | E8 | Issue credentials securely on approval | 4 | Given the credential has an expiry, when the expiry approaches, then I and the technical contact are notified in advance with instructions to rotate.
PRV-02 | E8 | Issue credentials securely on approval | 5 | Given a credential must be rotated, when I request rotation, then it follows the same secure issuance path without requiring a new onboarding request.
PRV-03 | E8 | See provisioning succeed or fail, and roll back cleanly | 1 | Given a request is approved, when provisioning runs, then its status moves through Provisioning to either Live or Provisioning Failed.
PRV-03 | E8 | See provisioning succeed or fail, and roll back cleanly | 2 | Given provisioning fails, when the failure occurs, then any partial configuration is rolled back, the approver and requester are notified, and the failure reason is displayed.
PRV-03 | E8 | See provisioning succeed or fail, and roll back cleanly | 3 | Given provisioning succeeds, when the status becomes Live, then a connectivity smoke test result is recorded against the interface.
PRV-03 | E8 | See provisioning succeed or fail, and roll back cleanly | 4 | Given the smoke test fails, when the result is recorded, then the interface is flagged as Live (Unverified) rather than being silently marked healthy.
AUD-01 | E9 | Maintain an immutable audit trail | 1 | Given any state transition, decision, override, reassignment or credential issuance occurs, when it commits, then an audit record is written capturing actor, role, action, timestamp, request reference and rationale.
AUD-01 | E9 | Maintain an immutable audit trail | 2 | And audit records are append-only; no user, including an administrator, can edit or delete one through any interface.
AUD-01 | E9 | Maintain an immutable audit trail | 3 | And the audit trail records failed authorisation attempts as well as successful actions.
AUD-01 | E9 | Maintain an immutable audit trail | 4 | Given an auditor needs evidence, when they export the trail for a request or a date range, then a complete, tamper-evident export is produced.
AUD-01 | E9 | Maintain an immutable audit trail | 5 | Given the retention policy applies, when the retention period elapses, then records are archived, not destroyed, unless destruction is explicitly mandated.
AUD-02 | E9 | Report on throughput, SLA and rejection reasons | 1 | Given I open reporting, when it loads, then I see requests submitted, approved, rejected and withdrawn over a selectable period, split by MFT and API.
AUD-02 | E9 | Report on throughput, SLA and rejection reasons | 2 | And I see median and 90th-percentile time-to-decision against SLA, with time spent Awaiting Information excluded.
AUD-02 | E9 | Report on throughput, SLA and rejection reasons | 3 | And I see rejection reason codes ranked by frequency, so that the commonest causes can be designed out of the form.
AUD-02 | E9 | Report on throughput, SLA and rejection reasons | 4 | And I see the proportion of requests requiring enhanced review and the proportion carrying anti-pattern overrides.
AUD-02 | E9 | Report on throughput, SLA and rejection reasons | 5 | Given I need the underlying data, when I select export, then I can download the dataset.
NFR-01 | E9 | Meet accessibility standards | 1 | Given the portal is assessed, when it is tested, then it conforms to WCAG 2.2 Level AA.
NFR-01 | E9 | Meet accessibility standards | 2 | And every function, including the full request forms, review screens and decision actions, is completable by keyboard alone.
NFR-01 | E9 | Meet accessibility standards | 3 | And every form error is announced by a screen reader and associated programmatically with the field it concerns.
NFR-01 | E9 | Meet accessibility standards | 4 | And no meaning is conveyed by colour alone — risk badges and SLA warnings carry a text or icon equivalent.
NFR-02 | E9 | Meet performance and availability targets | 1 | Given normal load, when I load any page, then it renders within the agreed response-time budget at the 95th percentile.
NFR-02 | E9 | Meet performance and availability targets | 2 | Given the approval queue contains a large number of requests, when it loads, then it pages and filters server-side rather than degrading.
NFR-02 | E9 | Meet performance and availability targets | 3 | Given the portal is unavailable, when the outage occurs, then no in-flight request data is lost and drafts survive.
NFR-02 | E9 | Meet performance and availability targets | 4 | Given the service level is defined, when availability is measured, then it is reported against the agreed SLO in the reporting view (AUD-02).