## Read me
Boomi MFT MVP, Two-week delivery plan
Candidate: ADR.040 Migrant Workers Scan, internal and external in one feed
Build window: Monday 28 September to Friday 9 October 2026
Version | v0.3 ¦ Draft for approval ¦ 8 September 2026
What this is | The working tracker for the two-week MVP. Black-header columns come from the plan. Green-header columns are yours to fill as the work runs.
Do this today | 1. Send the Endpoint details tab to the source, destination and ONS contacts. A complete return is the trigger to open the build window. 2. Raise the firewall, allow-list and ONS endpoint requests. They cannot be compressed by working harder. 3. Get option 1 agreed on the Data Lake options tab.
The order of the week | Discovery days 1 to 2. Connectivity days 1 to 4, in parallel. Configuration days 5 to 6, and that is the only build. Testing days 7 to 8. Readiness days 9 to 10.
The criterion that decides it | SC-3. Both legs delivered as configuration rows on one engine, zero bespoke components. Everything else is fixable.
Data Lake position | Option 1 is recommended: build now against the current ADR endpoints and re-point to the Data Lake as a configuration change when the warehouse migrates. Option 2, waiting for the migration, hands the start date to another programme.

## Executive view
Executive view
The whole argument on one screen. Detail sits in the tabs to the right.
Question | Answer
What we are doing | Moving one live feed off its legacy transfer mechanisms onto Boomi MFT, and evidencing the result well enough for a go or no-go decision.
On what | Feed ADR.040, the quarterly Migrant Workers Scan. It is the only feed identified that carries both patterns in a single business flow: NPS to ADR internal, and ADR to ONS external.
When | Monday 28 September to Friday 9 October 2026. Configuration is two days of that.
What it costs | Two days of build effort plus about a week of discovery, testing and handover around it. No new components, no new interfaces to maintain.
What we need before it starts | Three things, all before 28 September: the endpoint details in section 3, the firewall and allow-list changes raised, and agreement from ONS to receive from a new sending endpoint.
What good looks like | Both legs running as configuration rows on one generic engine, zero bespoke components, and Service Operations signing the handover.
Why it matters beyond this feed | If two similar transfers can both be delivered as configuration, onboarding the rest of the estate is configuration work rather than development work. That is the assumption the wider business case rests on, and it has not been tested.
What could stop it | Firewall lead time and the ONS agreement. Neither compresses by working harder. If ONS is not ready in time, leg A still delivers inside the window and leg B follows within days of the external path opening.
On the Data Lake migration | Build now against the current ADR endpoints and re-point to the Data Lake as a configuration change when the warehouse migrates. Option 1 in section 5. Waiting hands our start date to another programme.
Decision requested | Approve the window, name owners on the three critical dependencies, and agree option 1.

## Endpoint details
Endpoint details required, the whole of discovery
Fill every cell. A complete return is the gate into day 3. Send this tab to the source, destination and ONS contacts now, ahead of the window.
What we need | Leg A, source, NPS | Leg A, target, ADR landing | Leg B, source, ADR output | Leg B, target, ONS | Returned by | Date
Host and port
Protocol, SFTP, FTPS, S3 or share
Directory path
File name or mask
Credential type and who issues it
Host key or certificate
Firewall change needed, which direction
Source IP the far side must allow
Archive path
Quarantine path
Acknowledgement expected
Named contact

## Plan
Ten working days, five phases
Phase | Days | What happens | Done when | Owner | Status | Actual | Notes
1. Discovery | Day 1 to 2, 28 to 29 Sep | Capture the endpoint details in section 3 for both legs. Nothing else. No process mapping, no workshops. | Every cell in the endpoint table is filled
2. Connectivity | Day 1 to 4, 28 Sep to 1 Oct | Runs in parallel from day one. Firewall and allow-list changes, credentials, host keys, and a reachability test in both directions. | A test file moves end to end on both paths, manually
3. Configuration | Day 5 to 6, 2 and 5 Oct | Build MFT-INT-001 and MFT-EXT-001 as configuration rows on the generic engine. Schedule, file mask, archive, quarantine, alerts. | Both rows built, engine gap log empty
4. Testing | Day 7 to 8, 6 and 7 Oct | Happy path, file absent, late arrival, duplicate, oversized, scan failure, destination unavailable, credential rejection. Reconcile against the incumbent. | All cases evidenced, output byte identical
5. Readiness | Day 9 to 10, 8 and 9 Oct | Runbook, alerts and escalation. Walk Service Operations through one live failure and recovery. Prove and time the rollback. | Operations sign the handover, go or no-go issued

## Dependencies
Dependencies
The first three rows decide the start date. Everything else is ordinary.
Dependency | Owner | Needed by | Why it matters | Owner name | Raised on | Status | Notes
Endpoint details, all four columns in section 3 | Feed and system owners | Before day 1 | Discovery is two days only because this arrives complete. If it does not, day 1 becomes chasing, and the window slips
Firewall and allow-list changes, both legs | Network security | Raise now | The one item that cannot be compressed by working harder. Standard lead time is longer than the build itself, so it must be raised before the window opens
ONS agreement to receive from a new sending endpoint | Cross-department liaison | Raise now | Leg B cannot be proven without it. If it is not in place, leg A still delivers inside the window and leg B follows
ADR to Data Lake migration, agree option 1 | Data Lake programme | Before day 5 | See section 5. Option 1 lets the build start on time and treats the re-point as a configuration change
Credentials and host keys | Security architecture | Day 3 | Needed for the connectivity test, not for the build
Runtime placement approval | Platform engineering | Day 3 | Where the MFT runtime sits for each leg
Representative or synthetic test file | Feed owner, ADR | Day 6 | Testing needs a file with production structure, not production data
Service Operations availability, half a day | Service Operations | Day 9 | The handover walkthrough is what turns a demo into an accepted service
Incumbent path stays live throughout | Incumbent service owner | Day 1 | The MVP runs alongside, it does not cut over

## Data Lake options
ADR to Data Lake migration, option 1 recommended
Option 1: build now against the current ADR endpoints, re-point to the Data Lake as a configuration change when the warehouse migrates. Option 2: wait for the migration and build once. Recommendation is option 1, because option 2 hands the MVP start date to another programme.
| Option 1, recommended | Option 2 | Decision | Decided by | Date
What we do | Migrate the integration now. Move the transfer off legacy IAF onto Boomi, pointing at the existing ADR database and file areas. Re-point to the Data Lake as a configuration change when the warehouse migrates. | Wait for the warehouse migration to complete, then build once directly against the Data Lake endpoints.
Start date | 28 September. Nothing is gated on the Data Lake programme. | Whenever the warehouse migration lands. Not ours to set.
Build effort | Two days now, plus a one-row endpoint change later. | Two days, once.
What it proves | Both the transfer and the claim that re-pointing an interface is a configuration change rather than a rebuild. | The transfer only.
What it costs | One config change at migration time, and a short period where the flow points at an endpoint with a known end date. | The legacy IAF transfer keeps running on the old platform for the whole duration of the warehouse migration, and the MVP evidence arrives too late to inform the wider onboarding plan.
Main risk | The Data Lake endpoint differs enough that the re-point is not a one-row change. If so, that is a finding worth having early rather than late. | The migration slips and the MVP slips with it.

## Data Lake conditions
Conditions on option 1
Condition | Owner | Needed by | Owner name | Status | Answer
Confirm the NPS landing area and MWS output area are in migration scope, and the indicative move date | Data Lake programme | Day 5
Record the Data Lake target endpoints in the configuration row as a known future change, so the re-point is planned rather than discovered | Integration architecture | Day 6
Confirm whether the Maestro chain survives the migration or is replaced by Data Lake ingestion. If replaced, leg A's handover point moves | Data Lake programme | Day 5
Measure and record the re-point when it happens, as evidence for or against the one-row claim | Integration architecture | At migration

## Success criteria
Success criteria
Ref | Met when | Status | Evidence reference | Assessed by | Date
SC-1 | Leg A delivers into the ADR landing area, byte identical, three consecutive runs
SC-2 | Leg B delivers to ONS, acknowledged, three consecutive runs
SC-3 | Both legs are configuration rows on one engine, zero bespoke components
SC-4 | The existing Maestro chain runs unchanged after Boomi delivers
SC-5 | The Insecure IF server hop is absent from the leg B path
SC-6 | Non-arrival, transfer failure and scan failure each raise an alert to a named queue, evidenced in test
SC-7 | One audit record per transfer: source, destination, size, checksum, timestamps, outcome
SC-8 | Service Operations signs the handover after a live failure and recovery walkthrough
SC-9 | Rollback to the incumbent path executed and timed at least once
SC-10 | Build effort recorded in hours, separated from time spent waiting on dependencies

## Risks
What could move the date
Risk | What we do about it | Owner | Status | Notes
Firewall change is not complete by day 4 | Raise it now, before the window opens. If it lands late, connectivity slides and everything after it slides with it. This is the single most likely cause of a miss
ONS endpoint is not agreed in time | Split the result. Deliver leg A inside the window and report it. Leg B follows within days of the external path opening, because the build is already done
Endpoint details arrive incomplete | Day 1 and 2 become chasing. Send the section 3 table out now and treat a complete return as the trigger to open the window
Data Lake migration answers are unclear at day 5 | Proceed on option 1. Build to the current endpoints and record the re-point as a planned one-row change. Do not pause the build waiting for the migration plan
No production-like test environment | Test on the real path with a synthetic file. Say so plainly in the evidence rather than claiming coverage we do not have