## How to use
Boomi MFT MVP: Concept Note Review
Reviewed: Boomi Managed File Transfer MVP, Executive Concept Note, Draft v0.2 (9 September 2026)
Review v1.0 and suggested redraft v0.3 (draft), 20 October 2026
Purpose
Test and evidence catalogue for the four Boomi MFT MVP patterns, with review findings, decisions, dependencies and risks for the concept note.
How to use
1. Close the decisions on the Decisions sheet first. D-MVP-01 and D-MVP-05 decide which AV tests apply to P1, P2 and P4.
2. On Test catalogue, set Status for each test and fill Run date, Tester and Evidence link. Mark AV tests Not applicable where AV does not run on that pattern.
3. Summary and Success criteria update themselves from the Status column. A criterion shows Met only when every linked test is Passed or Not applicable.
4. Record your response to each review finding on Review findings.
Legend
Yellow cells are for you to fill in. All other cells are reference data or formulas.
Example of a completed test row
P3-TC-06 ¦ Status: Passed ¦ Run date: 03/11/2026 ¦ Tester: Test Lead ¦ Evidence link: evidence/P3-TC-06-alert.png ¦ Notes: Quarantined in 40 s, alert received in 2 min.
Assumed targets (to confirm under D-MVP-07): five consecutive scheduled runs per pattern; alert within 15 minutes; AV limit about 250 MB (G-15).

## Summary
Pattern | Tests | Passed | Failed | Blocked | Not applicable | Not run | Complete %
P1 External to external | 15 | 0 | 0 | 0 | 0 | 15 | 0%
P2 Internal to internal | 15 | 0 | 0 | 0 | 0 | 15 | 0%
P3 External to internal | 15 | 0 | 0 | 0 | 0 | 15 | 0%
P4 Internal to external | 15 | 0 | 0 | 0 | 0 | 15 | 0%
All (platform) | 10 | 0 | 0 | 0 | 0 | 10 | 0%
Total | 70 | 0 | 0 | 0 | 0 | 70 | 0%
Review findings by severity
High | 6
Medium | 14
Low | 6
Success criteria met | 0

## Test catalogue
Test ID | Pattern | Category | Scenario | Steps | Expected result | Success criteria | Evidence required | Priority | Status | Run date | Tester | Evidence link | Notes
P1-TC-01 | P1 External to external | Positive | Scheduled transfer, single file | Place one test file at source; wait for schedule. | File at target; SHA-256 matches source; audit record complete. | SC-1, SC-5 | Audit record, checksum comparison | Must | Not run
P1-TC-02 | P1 External to external | Positive | API-triggered transfer, single file | Call the trigger API with the agreed client and auth. | File at target; SHA-256 matches; audit record shows API trigger. | SC-1, SC-5 | API response, audit record | Must | Not run
P1-TC-03 | P1 External to external | Positive | Multiple files in one run | Place five files at source; run. | All five delivered; one audit record each. | SC-1, SC-5 | Audit extract | Should | Not run
P1-TC-04 | P1 External to external | Positive | Consecutive scheduled runs | Leave schedule running for five cycles with new files each cycle. | Five successful runs, no manual intervention. | SC-2 | Transfer history screenshot or export | Must | Not run
P1-TC-05 | P1 External to external | Positive | Source handling after transfer | Check source after a successful run. | Source file deleted, archived or kept as per D-MVP-08. | SC-1 | Source listing before and after | Should | Not run
P1-TC-06 | P1 External to external | Negative | Infected file (EICAR test file) | Place EICAR test file at source. | File quarantined, not delivered; alert raised; audit outcome shows quarantine. | SC-3, SC-4 | Alert, audit record, target listing | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P1-TC-07 | P1 External to external | Negative | AV service unavailable | Stop or block the AV service, then run. | Transfer held (fail closed); alert raised; nothing delivered unscanned. | SC-3, SC-4 | Alert, audit record | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P1-TC-08 | P1 External to external | Negative | Target unavailable or credentials rejected | Block target or rotate target credentials, then run. | Retries per policy, then failure alert; no partial file at target. | SC-3 | Alert, retry log, target listing | Must | Not run
P1-TC-09 | P1 External to external | Negative | Non-arrival | Leave source empty through the expected window. | Non-arrival alert raised within target time. | SC-3 | Alert with timestamp | Must | Not run
P1-TC-10 | P1 External to external | Negative | Zero-byte file | Place a zero-byte file at source. | Handled per agreed rule (reject or transfer) with audit outcome. | SC-5 | Audit record | Should | Not run
P1-TC-11 | P1 External to external | Negative | File name breaks naming rule | Place a file with an invalid name. | Not transferred; alert or audit outcome shows rejection. | SC-3, SC-5 | Audit record | Should | Not run
P1-TC-12 | P1 External to external | Negative | Duplicate file name at target | Send a file whose name already exists at target. | Handled per agreed rule (overwrite, version or reject) with audit. | SC-5 | Target listing, audit record | Should | Not run
P1-TC-13 | P1 External to external | Negative | File above AV size limit (G-15) | Place a file larger than the AV limit (about 250 MB). | Deterministic outcome per D-MVP-05; never delivered unscanned; alert raised. | SC-4 | Alert, audit record | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P1-TC-14 | P1 External to external | Positive | Largest permitted file within AV limit | Transfer a file just under the AV limit. | Delivered and scanned; duration recorded for sizing. | SC-1 | Audit record with timings | Should | Not run
P1-TC-15 | P1 External to external | Negative | Interrupted transfer | Drop the network mid-transfer. | Resume or restart; no corrupt or partial file left at target. | SC-1, SC-3 | Target checksum, audit record | Should | Not run
P2-TC-01 | P2 Internal to internal | Positive | Scheduled transfer, single file | Place one test file at source; wait for schedule. | File at target; SHA-256 matches source; audit record complete. | SC-1, SC-5 | Audit record, checksum comparison | Must | Not run
P2-TC-02 | P2 Internal to internal | Positive | API-triggered transfer, single file | Call the trigger API with the agreed client and auth. | File at target; SHA-256 matches; audit record shows API trigger. | SC-1, SC-5 | API response, audit record | Must | Not run
P2-TC-03 | P2 Internal to internal | Positive | Multiple files in one run | Place five files at source; run. | All five delivered; one audit record each. | SC-1, SC-5 | Audit extract | Should | Not run
P2-TC-04 | P2 Internal to internal | Positive | Consecutive scheduled runs | Leave schedule running for five cycles with new files each cycle. | Five successful runs, no manual intervention. | SC-2 | Transfer history screenshot or export | Must | Not run
P2-TC-05 | P2 Internal to internal | Positive | Source handling after transfer | Check source after a successful run. | Source file deleted, archived or kept as per D-MVP-08. | SC-1 | Source listing before and after | Should | Not run
P2-TC-06 | P2 Internal to internal | Negative | Infected file (EICAR test file) | Place EICAR test file at source. | File quarantined, not delivered; alert raised; audit outcome shows quarantine. | SC-3, SC-4 | Alert, audit record, target listing | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P2-TC-07 | P2 Internal to internal | Negative | AV service unavailable | Stop or block the AV service, then run. | Transfer held (fail closed); alert raised; nothing delivered unscanned. | SC-3, SC-4 | Alert, audit record | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P2-TC-08 | P2 Internal to internal | Negative | Target unavailable or credentials rejected | Block target or rotate target credentials, then run. | Retries per policy, then failure alert; no partial file at target. | SC-3 | Alert, retry log, target listing | Must | Not run
P2-TC-09 | P2 Internal to internal | Negative | Non-arrival | Leave source empty through the expected window. | Non-arrival alert raised within target time. | SC-3 | Alert with timestamp | Must | Not run
P2-TC-10 | P2 Internal to internal | Negative | Zero-byte file | Place a zero-byte file at source. | Handled per agreed rule (reject or transfer) with audit outcome. | SC-5 | Audit record | Should | Not run
P2-TC-11 | P2 Internal to internal | Negative | File name breaks naming rule | Place a file with an invalid name. | Not transferred; alert or audit outcome shows rejection. | SC-3, SC-5 | Audit record | Should | Not run
P2-TC-12 | P2 Internal to internal | Negative | Duplicate file name at target | Send a file whose name already exists at target. | Handled per agreed rule (overwrite, version or reject) with audit. | SC-5 | Target listing, audit record | Should | Not run
P2-TC-13 | P2 Internal to internal | Negative | File above AV size limit (G-15) | Place a file larger than the AV limit (about 250 MB). | Deterministic outcome per D-MVP-05; never delivered unscanned; alert raised. | SC-4 | Alert, audit record | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P2-TC-14 | P2 Internal to internal | Positive | Largest permitted file within AV limit | Transfer a file just under the AV limit. | Delivered and scanned; duration recorded for sizing. | SC-1 | Audit record with timings | Should | Not run
P2-TC-15 | P2 Internal to internal | Negative | Interrupted transfer | Drop the network mid-transfer. | Resume or restart; no corrupt or partial file left at target. | SC-1, SC-3 | Target checksum, audit record | Should | Not run
P3-TC-01 | P3 External to internal | Positive | Scheduled transfer, single file | Place one test file at source; wait for schedule. | File at target; SHA-256 matches source; audit record complete. | SC-1, SC-5 | Audit record, checksum comparison | Must | Not run
P3-TC-02 | P3 External to internal | Positive | API-triggered transfer, single file | Call the trigger API with the agreed client and auth. | File at target; SHA-256 matches; audit record shows API trigger. | SC-1, SC-5 | API response, audit record | Must | Not run
P3-TC-03 | P3 External to internal | Positive | Multiple files in one run | Place five files at source; run. | All five delivered; one audit record each. | SC-1, SC-5 | Audit extract | Should | Not run
P3-TC-04 | P3 External to internal | Positive | Consecutive scheduled runs | Leave schedule running for five cycles with new files each cycle. | Five successful runs, no manual intervention. | SC-2 | Transfer history screenshot or export | Must | Not run
P3-TC-05 | P3 External to internal | Positive | Source handling after transfer | Check source after a successful run. | Source file deleted, archived or kept as per D-MVP-08. | SC-1 | Source listing before and after | Should | Not run
P3-TC-06 | P3 External to internal | Negative | Infected file (EICAR test file) | Place EICAR test file at source. | File quarantined, not delivered; alert raised; audit outcome shows quarantine. | SC-3, SC-4 | Alert, audit record, target listing | Must | Not run
P3-TC-07 | P3 External to internal | Negative | AV service unavailable | Stop or block the AV service, then run. | Transfer held (fail closed); alert raised; nothing delivered unscanned. | SC-3, SC-4 | Alert, audit record | Must | Not run
P3-TC-08 | P3 External to internal | Negative | Target unavailable or credentials rejected | Block target or rotate target credentials, then run. | Retries per policy, then failure alert; no partial file at target. | SC-3 | Alert, retry log, target listing | Must | Not run
P3-TC-09 | P3 External to internal | Negative | Non-arrival | Leave source empty through the expected window. | Non-arrival alert raised within target time. | SC-3 | Alert with timestamp | Must | Not run
P3-TC-10 | P3 External to internal | Negative | Zero-byte file | Place a zero-byte file at source. | Handled per agreed rule (reject or transfer) with audit outcome. | SC-5 | Audit record | Should | Not run
P3-TC-11 | P3 External to internal | Negative | File name breaks naming rule | Place a file with an invalid name. | Not transferred; alert or audit outcome shows rejection. | SC-3, SC-5 | Audit record | Should | Not run
P3-TC-12 | P3 External to internal | Negative | Duplicate file name at target | Send a file whose name already exists at target. | Handled per agreed rule (overwrite, version or reject) with audit. | SC-5 | Target listing, audit record | Should | Not run
P3-TC-13 | P3 External to internal | Negative | File above AV size limit (G-15) | Place a file larger than the AV limit (about 250 MB). | Deterministic outcome per D-MVP-05; never delivered unscanned; alert raised. | SC-4 | Alert, audit record | Must | Not run
P3-TC-14 | P3 External to internal | Positive | Largest permitted file within AV limit | Transfer a file just under the AV limit. | Delivered and scanned; duration recorded for sizing. | SC-1 | Audit record with timings | Should | Not run
P3-TC-15 | P3 External to internal | Negative | Interrupted transfer | Drop the network mid-transfer. | Resume or restart; no corrupt or partial file left at target. | SC-1, SC-3 | Target checksum, audit record | Should | Not run
P4-TC-01 | P4 Internal to external | Positive | Scheduled transfer, single file | Place one test file at source; wait for schedule. | File at target; SHA-256 matches source; audit record complete. | SC-1, SC-5 | Audit record, checksum comparison | Must | Not run
P4-TC-02 | P4 Internal to external | Positive | API-triggered transfer, single file | Call the trigger API with the agreed client and auth. | File at target; SHA-256 matches; audit record shows API trigger. | SC-1, SC-5 | API response, audit record | Must | Not run
P4-TC-03 | P4 Internal to external | Positive | Multiple files in one run | Place five files at source; run. | All five delivered; one audit record each. | SC-1, SC-5 | Audit extract | Should | Not run
P4-TC-04 | P4 Internal to external | Positive | Consecutive scheduled runs | Leave schedule running for five cycles with new files each cycle. | Five successful runs, no manual intervention. | SC-2 | Transfer history screenshot or export | Must | Not run
P4-TC-05 | P4 Internal to external | Positive | Source handling after transfer | Check source after a successful run. | Source file deleted, archived or kept as per D-MVP-08. | SC-1 | Source listing before and after | Should | Not run
P4-TC-06 | P4 Internal to external | Negative | Infected file (EICAR test file) | Place EICAR test file at source. | File quarantined, not delivered; alert raised; audit outcome shows quarantine. | SC-3, SC-4 | Alert, audit record, target listing | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P4-TC-07 | P4 Internal to external | Negative | AV service unavailable | Stop or block the AV service, then run. | Transfer held (fail closed); alert raised; nothing delivered unscanned. | SC-3, SC-4 | Alert, audit record | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P4-TC-08 | P4 Internal to external | Negative | Target unavailable or credentials rejected | Block target or rotate target credentials, then run. | Retries per policy, then failure alert; no partial file at target. | SC-3 | Alert, retry log, target listing | Must | Not run
P4-TC-09 | P4 Internal to external | Negative | Non-arrival | Leave source empty through the expected window. | Non-arrival alert raised within target time. | SC-3 | Alert with timestamp | Must | Not run
P4-TC-10 | P4 Internal to external | Negative | Zero-byte file | Place a zero-byte file at source. | Handled per agreed rule (reject or transfer) with audit outcome. | SC-5 | Audit record | Should | Not run
P4-TC-11 | P4 Internal to external | Negative | File name breaks naming rule | Place a file with an invalid name. | Not transferred; alert or audit outcome shows rejection. | SC-3, SC-5 | Audit record | Should | Not run
P4-TC-12 | P4 Internal to external | Negative | Duplicate file name at target | Send a file whose name already exists at target. | Handled per agreed rule (overwrite, version or reject) with audit. | SC-5 | Target listing, audit record | Should | Not run
P4-TC-13 | P4 Internal to external | Negative | File above AV size limit (G-15) | Place a file larger than the AV limit (about 250 MB). | Deterministic outcome per D-MVP-05; never delivered unscanned; alert raised. | SC-4 | Alert, audit record | Must | Not run |  |  |  | Applies only if AV runs on this pattern (D-MVP-01, D-MVP-05).
P4-TC-14 | P4 Internal to external | Positive | Largest permitted file within AV limit | Transfer a file just under the AV limit. | Delivered and scanned; duration recorded for sizing. | SC-1 | Audit record with timings | Should | Not run
P4-TC-15 | P4 Internal to external | Negative | Interrupted transfer | Drop the network mid-transfer. | Resume or restart; no corrupt or partial file left at target. | SC-1, SC-3 | Target checksum, audit record | Should | Not run
PL-01 | All (platform) | Platform | Promote pattern configuration dev to test | See scenario. | Configuration in test matches dev with no re-keying. | SC-6 | Promotion record, config export | Must | Not run
PL-02 | All (platform) | Platform | Roll back a promoted configuration | See scenario. | Previous configuration restored, or gap recorded against G-13. | SC-6 | Rollback record or gap entry | Must | Not run
PL-03 | All (platform) | Platform | Credentials not visible in configuration or logs | See scenario. | No secrets in exports or logs; vault or interim control evidenced (G-14). | SC-7 | Config export, log sample | Must | Not run
PL-04 | All (platform) | Platform | TLS version on every leg | See scenario. | TLS 1.2 or higher on Pega, Boomi Cloud, Local Node and S3 legs. | SC-7 | Connection test output | Must | Not run
PL-05 | All (platform) | Platform | Encryption at rest on S3 | See scenario. | Bucket encryption with the agreed KMS key. | SC-7 | Bucket policy and encryption settings | Must | Not run
PL-06 | All (platform) | Platform | Least-privilege IAM for the Local Node | See scenario. | Role can only read source and write target prefixes. | SC-7 | IAM policy, denied-access test | Must | Not run
PL-07 | All (platform) | Platform | Audit extract for all MVP runs | See scenario. | Every run has all SC-5 fields; export usable by an auditor. | SC-5 | Audit export | Must | Not run
PL-08 | All (platform) | Platform | Role-based access in Boomi MFT | See scenario. | Operator cannot change configuration; admin can. | SC-7 | Access test record | Should | Not run
PL-09 | All (platform) | Platform | Alert routing reaches the agreed channel | See scenario. | Alerts land in the channel within target time. | SC-3 | Alert timestamps | Must | Not run
PL-10 | All (platform) | Platform | Runbook walk-through | See scenario. | Support restarts, replays and investigates a quarantined file unaided. | SC-8 | Walk-through record | Must | Not run

## Success criteria
ID | Criterion | Source in v0.2 | Linked tests | Passed or N/A | Status
SC-1 | Each of the four patterns completes a scheduled and an API-triggered transfer, and the target SHA-256 matches the source. | Original 1 | 24 | 0 | Not yet
SC-2 | Scheduled transfers run for at least five consecutive cycles per pattern with no manual intervention, and transfer history is visible end to end. | Original 2 | 4 | 0 | Not yet
SC-3 | Non-arrival, transfer failure, AV detection and AV service failure each raise an alert to the agreed channel within the agreed time (target 15 minutes, D-MVP-07). | Original 3, split | 25 | 0 | Not yet
SC-4 | An infected, unscannable or oversize file is never delivered to any target. | New | 12 | 0 | Not yet
SC-5 | Every transfer creates an audit record with source, destination, file name, size, SHA-256, start and end timestamps, outcome and correlation ID. | Original 4 | 25 | 0 | Not yet
SC-6 | Configuration is promoted from dev to test through the agreed mechanism with no manual re-keying; rollback is demonstrated or the gap is recorded against G-13. | New | 2 | 0 | Not yet
SC-7 | Security controls are evidenced: TLS 1.2 or higher on every leg, credentials held outside configuration (or the G-14 interim control recorded), least-privilege IAM on S3, encryption at rest. | New | 5 | 0 | Not yet
SC-8 | The support team can restart a failed transfer, replay a transfer and investigate a quarantined file using the draft runbook, without platform team help. | New | 1 | 0 | Not yet

## Patterns
ID | Pattern | Source | Target | Route | Boundary | AV | What it proves
P1 | External to external | Pega LZ 1 | Pega LZ 2 | Pega LZ 1 > Boomi MFT Cloud > Pega LZ 2 (or via Local Node if AV must apply, D-MVP-01) | Stays outside the internal estate unless routed through the Local Node | Only if routed through the Local Node (D-MVP-01, D-MVP-05) | SaaS to SaaS brokering without internal storage; partner-to-partner routing
P2 | Internal to internal | S3 bucket 1 | S3 bucket 2 | S3 bucket 1 > Boomi MFT Local Node > S3 bucket 2 | Inside the internal AWS boundary only | Per policy (D-MVP-05) | Internal movement, IAM least privilege, encryption at rest, scheduling
P3 | External to internal | Pega LZ 1 | S3 bucket 1 | Pega LZ 1 > Boomi MFT Cloud > Local Node > AV scan > S3 bucket 1 | Inbound trust boundary crossing | Mandatory before the file lands internally | Inbound boundary crossing, AV before landing, quarantine, firewall rules
P4 | Internal to external | S3 bucket 2 | Pega LZ 2 | S3 bucket 2 > Local Node > Boomi MFT Cloud > Pega LZ 2 | Outbound trust boundary crossing | Per policy for outbound (D-MVP-05) | Outbound egress controls, data classification check, partner delivery

## Review findings
ID | Section | Severity | Finding | Recommendation | Author response | Status
F-01 | Document control | Medium | Still v0.2 dated 9 September 2026. The scope change from the earlier single-feed candidate to four platform patterns is not recorded. | Issue v0.3 dated 20 October 2026 with a one-line change note, and record the scope change as a decision with a named owner. |  | Open
F-02 | 1. Objective | Low | Objective repeats the proposition and has nothing measurable. | Tie it to the four patterns and both trust-boundary directions, and point to the success criteria. |  | Open
F-03 | 2. Chosen use case | Low | 'Non-Live/Non-Prod interface' suggests a single named interface, which no longer applies. | Use 'Non-production environment; four platform transfer patterns; no live interface'. |  | Open
F-04 | 2. Chosen use case | Medium | External landing zone gives no access method, tenant or count. Pattern 1 needs two distinct external locations. | Name Pega LZ 1 and Pega LZ 2, state the access protocol (to confirm, D-MVP-02) and the owner. |  | Open
F-05 | 2. Chosen use case and 7 | Medium | Internal landing zone is a single 'S3 bucket'. Pattern 2 needs a separate source and target. | Name S3 bucket 1 and S3 bucket 2 (or two prefixes with separate IAM policies, D-MVP-03). |  | Open
F-06 | Diagram | High | Both Pega boxes are labelled 'Landing Zone 1' and both buckets 'S3 bucket 1', so Patterns 1 and 2 read as transfers into the same place. | Relabel as Pega LZ 1, Pega LZ 2, S3 bucket 1, S3 bucket 2. |  | Open
F-07 | Diagram | High | Dashed pattern lines run endpoint to endpoint and bypass Boomi. Solid lines only point towards Boomi MFT Cloud, so outbound routes (P1, P4) are not shown. | Show the physical route through Boomi for each pattern, with a legend separating route from pattern. See the corrected diagram. |  | Open
F-08 | Diagram and 5 | High | The note does not say which runtime runs each pattern. If P1 runs on Boomi MFT Cloud alone, the file never reaches the internally hosted AV and passes through Boomi-hosted infrastructure. | Add decision D-MVP-01 (runtime per pattern and where AV runs). State the data classification position for any cloud-only route. |  | Open
F-09 | 3. What the MVP will prove | Low | AV appears in both columns; 'Monitoring and alerting failure' does not read; scheduling, API trigger and CI/CD (all in scope) are missing. | Restructure into four themes: secure transfer, operability, repeatable delivery, audit and governance. |  | Open
F-10 | 4. Scope boundaries | Medium | 'Redesign of the retained downstream job chain' belongs to the earlier single-feed candidate and has no meaning for platform patterns. | Remove it. |  | Open
F-11 | 4. Scope boundaries | Medium | Out of scope list omits items reviewers will ask about: live data, performance and volume, HA and DR failover, payload encryption (PGP), production go-live. | Add them explicitly, or move any you want tested into scope (D-MVP-10 for PGP). |  | Open
F-12 | 4. Scope boundaries | Medium | API-triggered transfer is in scope but no caller or authentication is named. | Name the test client (for example a Postman collection against the Boomi API) and its auth method (D-MVP-09). |  | Open
F-13 | 4 and 6 | High | CI/CD promotion is in scope, but there is no native pipeline for MFT configuration (G-13) and no success criterion for it. | Add SC-6: promote dev to test through the agreed mechanism with no re-keying; demonstrate rollback or record the gap (D-MVP-06). |  | Open
F-14 | 5. Dependencies and decisions | Medium | Heading promises decisions but none are listed, and none have owners. | Add a decisions table with owner roles (D-MVP-01 to D-MVP-11). |  | Open
F-15 | 5. Dependencies and decisions | Medium | Missing dependencies: Pega side allow-listing of Boomi egress IPs and accounts, AWS IAM and KMS, credential storage (G-14), alert destination, MFT entitlement in non-production, security approval to connect non-production to external SaaS. | Add them as numbered dependencies with owners. |  | Open
F-16 | 5. Item 3 | Low | Sentence does not parse: 'test files confirmed file naming rules and confirmation of the data classification'. | 'Representative or synthetic test files agreed, with file naming rules and data classification confirmed.' |  | Open
F-17 | 6. Success criteria | High | 'Proven' is not defined, so criterion 1 cannot be signed off. | Define pass per pattern: scheduled and API run, target SHA-256 equals source, audit record complete. |  | Open
F-18 | 6. Success criteria | High | Negative-path testing is in scope but only three alerts are listed. No criterion that an infected or unscannable file is never delivered. | Add SC-4 and use the test catalogue (EICAR file, AV unavailable, target down, oversize file above the AV limit G-15, zero-byte, duplicate, bad name). |  | Open
F-19 | 6. Success criteria | Medium | 'Scan failure' could mean an infected file or a scanner fault. Both need testing and the behaviour differs. | Split into AV detection (quarantine) and AV service failure (fail closed). |  | Open
F-20 | 6. Success criteria | Medium | Security controls are in scope with no measurable criterion. | Add SC-7: TLS 1.2 or higher on every leg, credentials outside configuration, least-privilege IAM, encryption at rest. |  | Open
F-21 | 6. Success criteria | Medium | No measure for alert timeliness or for scheduling robustness. | Set a target (for example alert within 15 minutes, five consecutive scheduled runs per pattern), to confirm under D-MVP-07. |  | Open
F-22 | 7. Definition of done | Medium | No evidence pack, sign-off authority or gap treatment is named. | List the evidence pack, the sign-off roles and the rule that unmet criteria need an accepted gap with an owner. |  | Open
F-23 | 7. Definition of done | Low | 'Operational support capabilities' are not defined anywhere else in the note. | Name the runbook, alert routing and support walk-through (SC-8). |  | Open
F-24 | Not covered | Medium | Post-transfer handling of the source file (delete, archive, keep) is not stated. | Decide per pattern (D-MVP-08) and test it. |  | Open
F-25 | Not covered | Medium | No timeline, roles or risks. Readers cannot judge readiness or effort. | Add a short timeline, owner roles and the top risks (sections 8 and 9 of the redraft). |  | Open
F-26 | Header and footer | Low | Classification marking appears twice in the footer and once in the header. | Keep one marking in the header and one in the footer, per your document standard. |  | Open

## Decisions
ID | Decision required | Owner role | Outcome | Date | Status
D-MVP-01 | Runtime that executes each pattern (Boomi MFT Cloud or Local Node) and where AV scanning happens for each. | Boomi Platform Owner with Security Architect |  |  | Open
D-MVP-02 | Pega landing zone access method, accounts and keys, and confirmation that two distinct zones are available. | Pega Landing Zone Owner |  |  | Open
D-MVP-03 | Internal S3 layout (two buckets or two prefixes), IAM roles and KMS keys for the Local Node. | AWS Platform Owner |  |  | Open
D-MVP-04 | Credential storage for non-production: vault or PAM, or an interim control (G-14). | Security Architect |  |  | Open
D-MVP-05 | AV policy per pattern, maximum test file size against the AV limit (G-15, about 250 MB) and the behaviour for oversize files. | Boomi Platform Owner with Security Architect |  |  | Open
D-MVP-06 | Configuration promotion mechanism for dev to test and how rollback is evidenced (G-13). | Boomi Platform Owner |  |  | Open
D-MVP-07 | Alert channel for the MVP (email or Teams versus ServiceNow) and the alert response target. | Service Management Lead |  |  | Open
D-MVP-08 | Post-transfer handling of the source file (delete, archive or keep) and the retention period. | Integration Architect |  |  | Open
D-MVP-09 | API trigger client and its authentication method. | Integration Architect |  |  | Open
D-MVP-10 | Whether payload encryption (PGP) is in or out of MVP scope. | Security Architect |  |  | Open
D-MVP-11 | Sign-off authority for the evidence pack and the forum that receives the adoption recommendation. | Design Authority Chair |  |  | Open

## Dependencies
ID | Dependency | Owner role | Due | Status
DEP-01 | Boomi MFT runtimes available in non-production: Boomi MFT Cloud tenant and internally hosted Local Node, with AV (MDE) enabled. | Boomi Platform Owner |  | Open
DEP-02 | End-to-end connectivity: firewall and allow-list rules for Local Node to Boomi MFT Cloud, and Boomi egress IPs allow-listed on the Pega side. | Infrastructure Lead |  | Open
DEP-03 | Two Pega landing zones with accounts and keys for Boomi. | Pega Landing Zone Owner |  | Open
DEP-04 | Two S3 locations with IAM roles and KMS keys granted to the Local Node. | AWS Platform Owner |  | Open
DEP-05 | Representative or synthetic test files agreed, with file naming rules and data classification confirmed (including whether the data may be held in external SaaS). | Integration Architect with Data Owner |  | Open
DEP-06 | Credential storage arrangement agreed (D-MVP-04). | Security Architect |  | Open
DEP-07 | Alert destination set up and reachable (D-MVP-07). | Service Management Lead |  | Open
DEP-08 | Security approval to connect non-production to external SaaS. | Security Architect |  | Open

## Risks
ID | Risk | Impact / Likelihood | Mitigation | Owner role
R-MVP-01 | Firewall and allow-list lead times delay P3 and P4. | High / High | Raise change requests at note sign-off; test connectivity first. | Infrastructure Lead
R-MVP-02 | P1 routed through Boomi MFT Cloud bypasses internal AV; files above about 250 MB cannot be scanned (G-15). | High / Medium | Settle D-MVP-01 and D-MVP-05 before build; keep test files under the limit plus one oversize negative test. | Boomi Platform Owner
R-MVP-03 | No native CI/CD for MFT configuration (G-13), so SC-6 may not be met. | Medium / High | Agree the mechanism under D-MVP-06; record the gap if rollback cannot be shown. | Boomi Platform Owner
R-MVP-04 | No native PAM integration (G-14) leads to manual credential handling. | Medium / High | Interim controlled process with audit; record in the evidence pack. | Security Architect
R-MVP-05 | Pega landing zone access (two zones, accounts, keys) arrives late. | Medium / Medium | Confirm D-MVP-02 in week 0; P2 can start without it. | Pega Landing Zone Owner
R-MVP-06 | External SaaS may not accept representative data. | Medium / Medium | Default to synthetic files for P1, P3 and P4. | Integration Architect
R-MVP-07 | ServiceNow and Dynatrace are out of scope, so operational readiness is shown by email or Teams alerts only. | Low / High | State this limit in the recommendation. | Service Management Lead