## Read me
Boomi MFT Solution Design
Configuration specification, ADR.040 Migrant Workers Scan
Return completed sections by Friday 25 September 2026
Version | v1.0 ¦ Issued for completion by stakeholder teams ¦ 8 September 2026
What to do | Find the tab or tabs for your team on the Who fills what sheet. Fill in the columns with a green header. Leave the black-header columns alone, they are the specification.
If a row does not apply | Write not applicable. Do not leave it blank. A blank cell tells us nothing; not applicable tells us a decision was made.
If you do not know | Write who does. That is a useful answer.
Start with these | Tab D Leg B target and tab Network rules. The ONS endpoint and the firewall changes have the longest lead times in the whole design. Everything else can be chased during the build window; those two cannot.
The three rows that matter most | A-10, B-06 and C-06, on how we know a file is complete before we move it. Unanswered, these are the most common cause of corrupt or truncated transfers.
Return it to | Integration Architecture, by Friday 25 September 2026

## Who fills what
0. How to use this document
Section | Team that completes it | Needed by
3. Leg A source endpoint | NPS source system owner | Fri 25 Sep 2026
4. Leg A target endpoint | ADR warehouse and platform team | Fri 25 Sep 2026
5. Leg B source endpoint | ADR warehouse and platform team | Fri 25 Sep 2026
6. Leg B target endpoint | ONS, via cross-department liaison | Fri 25 Sep 2026
7. File specification | Feed owner, ADR | Fri 25 Sep 2026
8. Scheduling and triggering | Feed owner, ADR | Fri 25 Sep 2026
9. Network and firewall | Network security | Raise now, complete by 25 Sep
10. Security and credentials | Security architecture | Fri 25 Sep 2026
11. Error handling | Feed owner with Integration architecture | Fri 25 Sep 2026
12. Monitoring and alerting | Service Operations | Fri 25 Sep 2026
13. Non-functional requirements | Feed owner, ADR | Fri 25 Sep 2026
14. Environments and test data | Platform engineering with the feed owner | Fri 25 Sep 2026
15. Data Lake endpoint register | Data Lake programme | Fri 25 Sep 2026
16. Open questions | Anyone | Ongoing
17. Sign-off | All named owners | Fri 25 Sep 2026

## Flow inventory
2. Flow inventory
Flow ID | Pattern | Source | Target | Replaces
MFT-INT-001 | Internal to internal | NPS extract drop point | ADR NPS file landing area | UTM transfer
MFT-EXT-001 | Internal to external | ADR MWS file output area | ONS receiving endpoint | Maestro job 5, Insecure IF server and SDES

## A Leg A source
3. Leg A source endpoint
To be completed by: NPS source system owner Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
A-01 | Hostname or IP | The endpoint Boomi connects to | nps-ftp01.internal
A-02 | Protocol | Determines the connector and the security profile | SFTP, FTPS, SMB share, S3 or local file system
A-03 | Port | Needed for the firewall rule as well as the connection | 22
A-04 | Directory path | Where the file is written | /data/outbound/mws
A-05 | File name or mask | How Boomi identifies the right file | MWS_SCAN_YYYYMMDD.dat or MWS_SCAN_*.dat
A-06 | Authentication method | Drives credential provisioning | SSH key pair, username and password, or IAM role
A-07 | Service account name | The identity Boomi presents | svc-boomi-mft
A-08 | Host key fingerprint or server certificate | Prevents connecting to a spoofed endpoint. Required, not optional | SHA256:xxxxxxxx
A-09 | Who issues and rotates the credential | So rotation does not silently break the flow | Named team
A-10 | Is the file written atomically? | If not, Boomi can pick up a partial file. This is the single most common cause of corrupt transfers | Written to .tmp then renamed, or a done file is created
A-11 | Completion signal, if any | What tells us the file is finished being written | Trigger file, rename, or none
A-12 | After collection: leave, delete or move | Determines whether we can re-collect and whether we cause a duplicate | Move to archive
A-13 | Source archive path | Where the file goes after collection | /data/outbound/mws/archive
A-14 | Retention on source | How long we can go back to re-collect | 90 days
A-15 | Does the source need to allow-list our IPs? | If yes it goes into section 9 and starts a lead time now | Yes or no
A-16 | Named contact and out of hours route | Who we call when it does not arrive | Name, email, escalation

## B Leg A target
4. Leg A target endpoint
To be completed by: ADR warehouse and platform team Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
B-01 | Hostname or IP | The endpoint Boomi delivers to | adr-land01.internal
B-02 | Protocol | Connector and security profile | SFTP, SMB share or S3
B-03 | Port | Firewall rule and connection | 22
B-04 | Directory path | Exactly where Maestro job 1 looks | /adr/landing/nps
B-05 | Delivered file name | Whether we keep the source name or rename | Same as source, or a stated rule
B-06 | Write method | So Maestro never sees a partial file | Write to .tmp in the same directory then rename
B-07 | Authentication method | Credential provisioning | SSH key pair or service account
B-08 | Service account name | The identity Boomi presents | svc-boomi-mft
B-09 | Host key or certificate | Endpoint verification | SHA256:xxxxxxxx
B-10 | File permissions and ownership required | Maestro must be able to read and move the file | 0640, owner adrsvc
B-11 | What Maestro job 1 expects | Confirms we are delivering something the chain will actually detect | File name pattern and polling interval
B-12 | Duplicate handling | What we do if the same file arrives twice | Overwrite, reject, or suffix
B-13 | Does the target need to allow-list our IPs? | Feeds section 9 | Yes or no
B-14 | Named contact and out of hours route | Escalation on failure | Name, email, escalation

## C Leg B source
5. Leg B source endpoint
To be completed by: ADR warehouse and platform team Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
C-01 | Hostname or IP | Collection endpoint | adr-out01.internal
C-02 | Protocol | Connector and security profile | SFTP, SMB share or S3
C-03 | Port | Firewall rule and connection | 22
C-04 | Directory path | Where Maestro job 4 writes | /adr/output/mws
C-05 | File name or mask | How Boomi identifies the file | MWS_ONS_YYYYMMDD.dat
C-06 | How do we know extraction is complete? | The critical question on this leg. Collecting mid-write sends a truncated file to another department | Done file, rename, or a Maestro completion event
C-07 | Number of files per cycle | One file or a set. Changes the completion logic entirely | 1
C-08 | Authentication method | Credential provisioning | SSH key pair
C-09 | Service account name | Identity Boomi presents | svc-boomi-mft
C-10 | Host key or certificate | Endpoint verification | SHA256:xxxxxxxx
C-11 | After collection: leave, delete or move | Duplicate prevention | Move to archive
C-12 | Archive path and retention | Re-send capability | /adr/output/mws/archive, 90 days
C-13 | Named contact and out of hours route | Escalation on failure | Name, email, escalation

## D Leg B target
6. Leg B target endpoint
To be completed by: ONS, via the cross-department liaison Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
D-01 | Hostname or IP | Delivery endpoint | sftp.ons.gov.uk
D-02 | Protocol | Connector and security profile | SFTP
D-03 | Port | Firewall rule and connection | 22
D-04 | Directory path | Where the file must land | /incoming/dept/mws
D-05 | Required file name convention | Receiving systems usually enforce one | MWS_SCAN_YYYYMMDD.dat
D-06 | Authentication method | Drives the key exchange | SSH key pair, mutual TLS
D-07 | Account name and who issues it | Identity we present | Name and issuing team
D-08 | Host key fingerprint | So we verify we are talking to ONS | SHA256:xxxxxxxx
D-09 | Where do we send our public key, and to whom? | The exchange itself is often the longest single step | Named person and process
D-10 | Which of our egress IPs must ONS allow-list? | Their firewall change, on their lead time | IP or range
D-11 | Acknowledgement mechanism | How we know delivery succeeded rather than assuming it | Receipt file, email, portal, or none
D-12 | File level encryption required? | PGP is common for cross-department transfer. If yes, whose key and how is it exchanged | PGP, key ID
D-13 | Delivery window or cut-off | When the file must be there by | Within 5 working days of quarter start
D-14 | What happens on rejection, and how are we told? | Silent rejection is worse than failure | Process and contact
D-15 | Named contact and escalation route | Who we contact when a transfer fails | Name, email, escalation

## File spec
7. File specification
To be completed by: Feed owner, ADR Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
F-01 | Format | Determines whether any validation is possible | Fixed width, delimited, XML, JSON
F-02 | Character encoding | Prevents corruption on transfer | UTF-8, ISO-8859-1, EBCDIC
F-03 | Delimiter or record layout | Only needed if we validate structure | Pipe delimited
F-04 | Header and trailer records | Often carry control totals | Yes or no, and content
F-05 | Typical file size | Sizing and scan ceiling check | 120 MB
F-06 | Maximum plausible file size | The anti-virus scan ceiling is around 250 MB. If we can exceed it we need a design decision now | 300 MB
F-07 | Compression | Affects both size and scanning | None, gzip, zip
F-08 | Record count or control total available? | Lets us reconcile rather than just confirm bytes moved | Yes or no
F-09 | Checksum provided by the source? | The cleanest integrity check available | MD5, SHA256, none
F-10 | Does the file contain personal data? | Drives classification, handling and whether a DPIA is required | Yes or no
F-11 | Classification | Handling controls | OFFICIAL
F-12 | Retention in transit and archive | How long Boomi may hold a copy | 30 days

## Scheduling
8. Scheduling and triggering
To be completed by: Feed owner, ADR Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
S-01 | Trigger type | Schedule, event or manual | Scheduled poll
S-02 | Schedule for leg A | When Boomi starts looking | First day of Jan, Apr, Jul, Oct
S-03 | Schedule for leg B | When Boomi starts looking for the output | On completion of the internal chain, or a fixed offset
S-04 | Earliest and latest expected arrival | Defines the window inside which non-arrival is not yet a problem | Between 02:00 and 18:00 on the trigger date
S-05 | Maximum wait before escalation | Turns a silent non-arrival into an alert | 24 hours
S-06 | Poll interval within the window | How often Boomi checks | Every 15 minutes
S-07 | Retry policy on failure | Attempts and interval before we alert | 3 attempts, 10 minutes apart
S-08 | Behaviour on a missed cycle | Wait for the next quarter, or alert and hold | Alert and hold
S-09 | Calendar exceptions | Bank holidays and year end can move the trigger date | None, or stated rule

## Network rules
9. Network and firewall
To be completed by: Network security Needed by: Raise now, complete by Friday 25 September 2026
Ref | Leg | Direction | Source | Destination and port | Change ref | Status
N-01 | A | Boomi runtime to NPS source
N-02 | A | Boomi runtime to ADR landing area
N-03 | B | Boomi runtime to ADR output area
N-04 | B | Boomi runtime egress to ONS
N-05 | B | ONS inbound allow-list of our egress IPs
N-06 | Both | Boomi runtime to the anti-virus scanning service
N-07 | Both | Boomi runtime to the secrets store
Ref | Parameter | Why we need it | Example | Value
N-10 | Runtime placement, leg A | Which runtime executes the flow and where it sits | Named environment
N-11 | Runtime placement, leg B | May differ from leg A because of egress control | Named environment
N-12 | Egress IP or range presented to ONS | This is what ONS allow-lists. It must be stable | IP or range
N-13 | Proxy in the path? | Changes the connection profile and the host key verification | Yes or no
N-14 | Standard lead time for a change of this type | Sets the earliest date the window can open | Working days

## Security
10. Security and credentials
To be completed by: Security architecture Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
SEC-01 | Where are credentials stored? | There is no documented native path from MFT to the enterprise secrets store. If that holds, we need an interim control with an owner and a review date | Enterprise secrets store, or stated interim
SEC-02 | Interim control if the secrets store cannot be used | Recorded as a condition rather than left implicit | Control, owner, review date
SEC-03 | Key rotation period and process | Rotation that nobody plans for is how transfers break | Period and owner
SEC-04 | Minimum transport security accepted | Confirms the protocol and cipher choice is acceptable for an OFFICIAL feed crossing a departmental boundary | Protocol, cipher, key exchange
SEC-05 | Anti-virus scanning point | Where in the path the file is scanned | Named service
SEC-06 | Behaviour on scan failure | Quarantine and alert, never deliver | Quarantine and alert
SEC-07 | Behaviour when a file exceeds the scan ceiling | The ceiling is around 250 MB. Silent pass-through would be the worst outcome | Reject, alert, or alternative scan
SEC-08 | File level encryption requirement | Whether PGP or equivalent is required on leg B | Yes or no, and key detail
SEC-09 | Audit record retention | How long transfer evidence must be kept | Period
SEC-10 | DPIA position | Whether one is held, required or not applicable for this feed | Held, required or not applicable

## Error handling
11. Error handling
To be completed by: Feed owner with Integration architecture Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
E-01 | Quarantine path, leg A | Where a bad file goes instead of onward | /adr/quarantine/nps
E-02 | Quarantine path, leg B | Same, on the outbound side | /adr/quarantine/ons
E-03 | Who reviews quarantined files, and within what time? | A quarantine nobody empties is just a slower failure | Team and interval
E-04 | Zero byte file | Deliver, reject or hold | Reject and alert
E-05 | File smaller or larger than expected | A crude but effective correctness check | Thresholds, or none
E-06 | Duplicate file in the same cycle | Prevents sending the same data twice to another department | Reject and alert
E-07 | Partial transfer or connection loss mid-flight | Resume, restart or fail | Restart from the beginning
E-08 | Destination unavailable | How long we retry before declaring failure | Retry policy
E-09 | Credential rejection | Immediate alert, no silent retry loop | Alert immediately
E-10 | Manual re-send process and who may run it | Needed for the runbook | Process and authorised roles

## Monitoring
12. Monitoring and alerting
To be completed by: Service Operations Needed by: Friday 25 September 2026
Ref | Event | Severity | Alert to | Response expected
M-01 | File not arrived by the maximum wait
M-02 | Transfer failed after all retries
M-03 | Anti-virus scan failed
M-04 | File quarantined
M-05 | Credential rejected
M-06 | Destination unavailable
M-07 | Destination rejected a valid file
M-08 | Transfer completed successfully
Ref | Parameter | Why we need it | Example | Value
M-10 | Alert channel | Where alerts land | Named queue or tool
M-11 | Support hours for this feed | Quarterly feeds rarely justify out of hours, but it must be stated | Business hours
M-12 | Escalation path | Who after the first responder | Named roles
M-13 | Where the transfer audit record is viewed | Operations need one place to look | Named tool or dashboard

## NFRs
13. Non-functional requirements
To be completed by: Feed owner, ADR Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
NF-01 | Volume per cycle | Sizing | 1 file, 120 MB
NF-02 | Frequency | Sizing and scheduling | Quarterly
NF-03 | Acceptable transfer duration | When slow becomes a problem | Under 30 minutes
NF-04 | Business impact of a missed cycle | Determines how hard we chase it | Stated impact
NF-05 | How long can delivery be late before it matters? | Sets the real escalation clock | Days
NF-06 | Availability requirement | A quarterly feed does not need continuous availability, but say so | Best endeavours in business hours
NF-07 | Growth expectation over 3 years | Whether we are designing for today's file only | Percentage or none known

## Environments
14. Environments and test data
To be completed by: Platform engineering with the feed owner Needed by: Friday 25 September 2026
Ref | Parameter | Why we need it | Example | Value
EN-01 | Environments available for this build | Which we configure and in what order | Dev, test, production
EN-02 | Does non-production have realistic network topology? | Testing on a flat sandbox proves nothing about the real path | Yes or no
EN-03 | Non-production endpoints for each of the four in sections 3 to 6 | Otherwise testing has to happen in production | Hosts and paths
EN-04 | Test file: synthetic, anonymised or production copy | Determines what controls apply to the test itself | Synthetic preferred
EN-05 | Who provides the test file and by when | Testing starts on day 7 | Name and date
EN-06 | Is an infected test file permitted for scan testing? | Needed to prove the scanning control actually blocks | EICAR test file, yes or no
EN-07 | How configuration is promoted between environments | There is no native promotion pipeline. Manual promotion must be documented and signed | Process and approver

## Data Lake register
15. Data Lake endpoint register
To be completed by: Data Lake programme Needed by: Friday 25 September 2026
Ref | Endpoint | Current value | Future Data Lake value | Expected change date
DL-01 | Leg A target, NPS landing area | See section 4
DL-02 | Leg B source, MWS output area | See section 5
DL-03 | Maestro chain: survives or replaced by Data Lake ingestion?
DL-04 | Credential or account change at migration
DL-05 | Firewall change required at migration

## Open questions
16. Open questions
Ref | Question | Raised by | Owner | Answer | Date
Q-01
Q-02
Q-03
Q-04
Q-05

## Sign-off
17. Sign-off
Section | Role | Name | Date
3. Leg A source endpoint | NPS source system owner
4. Leg A target endpoint | ADR warehouse and platform team
5. Leg B source endpoint | ADR warehouse and platform team
6. Leg B target endpoint | Cross-department liaison, on behalf of ONS
7 and 8. File and scheduling | Feed owner, ADR
9. Network and firewall | Network security
10. Security and credentials | Security architecture
11 and 12. Error handling and monitoring | Service Operations
13 and 14. NFRs, environments and test data | Platform engineering
15. Data Lake endpoint register | Data Lake programme
Overall design | Integration architecture