## Step Tracker
Legend: edit only the yellow columns (Status, Owner, Notes). Status list: Not started, In progress, Blocked, Done.
Step ID | Phase | Track | Step | Dependencies | Success criteria | Lead role | Status | Owner (name) | Notes / evidence
P0.1 | Mobilise and confirm | Governance | Confirm ADR.040/041 as the MVP candidate and record the executive decision | D5, D7, D8 | - | MVP Lead / Service Owner | Not started
P0.2 | Mobilise and confirm | Governance | Name owners for business, DWIT, security, network, operations, Boomi implementation and 24x7 support | D5, D7, D8 | - | MVP Lead / Service Owner | Not started
P0.3 | Mobilise and confirm | Governance | Confirm data classification, file naming rules, typical and peak file sizes, and quarterly schedule | D5, D7, D8 | - | MVP Lead / Service Owner | Not started
P0.4 | Mobilise and confirm | Governance | Record decision D7: build against current ADR endpoints, re-point to Data Lake later as a configuration change | D5, D7, D8 | - | MVP Lead / Service Owner | Not started
P0.5 | Mobilise and confirm | Governance | Open a RAID log and decision log with named owners; agree go/no-go criteria up front (use SC1 to SC6) | D5, D7, D8 | - | MVP Lead / Service Owner | Not started
P1.1 | Environments and connectivity | Platform (critical path) | Confirm Dev, Test, Pre-prod and Prod MFT tenants and MFT CI/CD portal access | D1, D2, D3, D4, D6 | - | Platform Engineer / Network | Not started
P1.2 | Environments and connectivity | Platform (critical path) | Install and register organisation-hosted runtimes; confirm Windows Server hardening and Defender AV (D6) | D1, D2, D3, D4, D6 | - | Platform Engineer / Network | Not started
P1.3 | Environments and connectivity | Platform (critical path) | Raise firewall and allow-list changes for NPS, ADR and ONS in every environment (inbound and outbound, protocol and port) | D1, D2, D3, D4, D6 | - | Platform Engineer / Network | Not started
P1.4 | Environments and connectivity | Platform (critical path) | Agree with ONS the new sending endpoint, source IPs and a production-like lower environment | D1, D2, D3, D4, D6 | - | Platform Engineer / Network | Not started
P1.5 | Environments and connectivity | Platform (critical path) | Run a connectivity smoke test per endpoint per environment (TCP, protocol handshake, auth) and record evidence | D1, D2, D3, D4, D6 | - | Platform Engineer / Network | Not started
P2.1 | Security and credentials | Security | Exchange SSH host keys / certificates and pin them; agree key rotation ownership | D2, D3, D5, D6 | SC5, SC6 | Security Architect | Not started
P2.2 | Security and credentials | Security | Decide credential storage: native MFT vault now, or documented route to enterprise PAM (tracked gap G-14) | D2, D3, D5, D6 | SC5, SC6 | Security Architect | Not started
P2.3 | Security and credentials | Security | Confirm AV scanning point and behaviour on scan failure (quarantine, alert, no onward delivery) | D2, D3, D5, D6 | SC5, SC6 | Security Architect | Not started
P2.4 | Security and credentials | Security | Check feed file size against AV scan ceiling (about 250 MB, gap G-15); design split or exception if exceeded | D2, D3, D5, D6 | SC5, SC6 | Security Architect | Not started
P2.5 | Security and credentials | Security | Obtain security sign-off of the transfer design for the confirmed classification | D2, D3, D5, D6 | SC5, SC6 | Security Architect | Not started
P3.1 | Configure Leg A (NPS to ADR) | Build | Define source and target endpoints, file mask and naming rules | D1, D3, D5 | SC1, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P3.2 | Configure Leg A (NPS to ADR) | Build | Set schedule and non-arrival window aligned to the quarterly feed | D1, D3, D5 | SC1, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P3.3 | Configure Leg A (NPS to ADR) | Build | Configure AV scan, archive, quarantine, retry and checksum validation | D1, D3, D5 | SC1, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P3.4 | Configure Leg A (NPS to ADR) | Build | Configure alerts for non-arrival, transfer failure and scan failure to a named team | D1, D3, D5 | SC1, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P3.5 | Configure Leg A (NPS to ADR) | Build | Parameterise environment-specific values so promotion changes config, not design | D1, D3, D5 | SC1, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P4.1 | Configure Leg B (ADR to ONS) | Build | Define ADR output source and ONS external target with pinned host key / certificate | D3, D4, D5 | SC2, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P4.2 | Configure Leg B (ADR to ONS) | Build | Set trigger (schedule or event after Leg A processing chain completes) | D3, D4, D5 | SC2, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P4.3 | Configure Leg B (ADR to ONS) | Build | Configure AV scan, archive, quarantine, retry and checksum validation | D3, D4, D5 | SC2, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P4.4 | Configure Leg B (ADR to ONS) | Build | Agree and configure the ONS receipt acknowledgement method | D3, D4, D5 | SC2, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P4.5 | Configure Leg B (ADR to ONS) | Build | Configure alerts and audit record fields as per SC6 | D3, D4, D5 | SC2, SC4, SC5, SC6 | Boomi MFT Engineer | Not started
P5.1 | CI/CD promotion | Build | Package both leg configurations in the MFT CI/CD portal | D1 | SC3 | Platform Engineer | Not started
P5.2 | CI/CD promotion | Build | Define approval roles (requester, approver) and segregation of duties | D1 | SC3 | Platform Engineer | Not started
P5.3 | CI/CD promotion | Build | Promote Dev to Test to Pre-prod with environment overrides only | D1 | SC3 | Platform Engineer | Not started
P5.4 | CI/CD promotion | Build | Test and document rollback: config rows are data, so rollback is a re-promotion of the prior version (gap G-13) | D1 | SC3 | Platform Engineer | Not started
P5.5 | CI/CD promotion | Build | Capture promotion audit evidence for each step | D1 | SC3 | Platform Engineer | Not started
P6.1 | Observability and audit | Operate | Confirm transfer history view covers both legs end to end | D8 | SC4, SC5, SC6 | Operations Lead | Not started
P6.2 | Observability and audit | Operate | Verify audit record fields: source, destination, file size, checksum, timestamps, outcome | D8 | SC4, SC5, SC6 | Operations Lead | Not started
P6.3 | Observability and audit | Operate | Route alerts to the named team; ServiceNow or Dynatrace only if essential for readiness | D8 | SC4, SC5, SC6 | Operations Lead | Not started
P6.4 | Observability and audit | Operate | Define simple service KPIs: on-time delivery, failures, mean time to recover | D8 | SC4, SC5, SC6 | Operations Lead | Not started
P7.1 | Test | Assure | Positive: Leg A and Leg B end to end with representative file sizes | D4, D5 | SC1, SC2, SC3, SC4, SC5, SC6 | Test Lead | Not started
P7.2 | Test | Assure | Negative: non-arrival, target unavailable, credential failure, AV scan failure, checksum mismatch, duplicate file | D4, D5 | SC1, SC2, SC3, SC4, SC5, SC6 | Test Lead | Not started
P7.3 | Test | Assure | Recovery: retry, re-run from archive, release from quarantine | D4, D5 | SC1, SC2, SC3, SC4, SC5, SC6 | Test Lead | Not started
P7.4 | Test | Assure | Promotion and rollback test via CI/CD portal | D4, D5 | SC1, SC2, SC3, SC4, SC5, SC6 | Test Lead | Not started
P7.5 | Test | Assure | Collate a test evidence pack mapped to SC1 to SC6 | D4, D5 | SC1, SC2, SC3, SC4, SC5, SC6 | Test Lead | Not started
P8.1 | Prove in production and hand over | Operate | Promote to Prod through CI/CD with change approval | D8 | SC1, SC2, SC4, SC5, SC6 | Service Owner | Not started
P8.2 | Prove in production and hand over | Operate | Run the live quarterly transfer with hypercare and parallel check against the legacy route | D8 | SC1, SC2, SC4, SC5, SC6 | Service Owner | Not started
P8.3 | Prove in production and hand over | Operate | Decommission or disable the UTM and IF/SDES route once delivery is confirmed | D8 | SC1, SC2, SC4, SC5, SC6 | Service Owner | Not started
P8.4 | Prove in production and hand over | Operate | Hand over runbook, alert routing, support model and Boomi 24x7 escalation; run a support drill | D8 | SC1, SC2, SC4, SC5, SC6 | Service Owner | Not started
P8.5 | Prove in production and hand over | Operate | Obtain service acceptance from operations | D8 | SC1, SC2, SC4, SC5, SC6 | Service Owner | Not started
P9.1 | Go/no-go and scale recommendation | Governance | Score each success criterion with evidence | - | SC1, SC2, SC3, SC4, SC5, SC6 | MVP Lead | Not started
P9.2 | Go/no-go and scale recommendation | Governance | Record lessons learned, open gaps (G-13, G-14, G-15) and platform constraints | - | SC1, SC2, SC3, SC4, SC5, SC6 | MVP Lead | Not started
P9.3 | Go/no-go and scale recommendation | Governance | Define the onboarding pattern and template for the next feeds | - | SC1, SC2, SC3, SC4, SC5, SC6 | MVP Lead | Not started
P9.4 | Go/no-go and scale recommendation | Governance | Issue go/no-go and wider adoption recommendation to the executive sponsor | - | SC1, SC2, SC3, SC4, SC5, SC6 | MVP Lead | Not started

## Phase Summary
Phase ID | Phase | Exit gate | Steps | Done | % complete
P0 | Mobilise and confirm | Decision log signed off; owners named; file profile confirmed | 5 | 0 | 0%
P1 | Environments and connectivity | All endpoints reachable from runtime in lower environments with evidence | 5 | 0 | 0%
P2 | Security and credentials | Security design approved; credentials and keys in place | 5 | 0 | 0%
P3 | Configure Leg A (NPS to ADR) | Leg A runs in Dev with a synthetic file | 5 | 0 | 0%
P4 | Configure Leg B (ADR to ONS) | Leg B delivers to ONS lower environment with acknowledgement | 5 | 0 | 0%
P5 | CI/CD promotion | Both legs promoted to Pre-prod via approved pipeline with audit trail | 5 | 0 | 0%
P6 | Observability and audit | Dashboards and alerts demonstrated to operations | 4 | 0 | 0%
P7 | Test | Evidence pack reviewed; defects closed or accepted | 5 | 0 | 0%
P8 | Prove in production and hand over | Live feed delivered; service accepted by operations | 5 | 0 | 0%
P9 | Go/no-go and scale recommendation | Recommendation issued; definition of done met | 4 | 0 | 0%
| TOTAL |  | 48 | 0 | 0%

## Dependencies
ID | Dependency | Owner (name) | Status
D1 | Dev, Test, Pre-prod and Prod environments on Boomi SaaS MFT, including MFT CI/CD portal
D2 | Organisation-hosted Boomi runtimes with anti-virus capability
D3 | End-to-end connectivity, firewall and allow-list changes for NPS, ADR/Data Lake and ONS, with credentials, certificates and host keys
D4 | ONS agreement to receive from the new sending endpoint, plus a production-like lower environment
D5 | Representative or synthetic test files, confirmed file naming rules and data classification
D6 | Windows Server readiness including Microsoft Defender Antivirus and platform security controls
D7 | Decision on ADR-to-Data Lake migration (recommended: build against available endpoint, re-point by configuration)
D8 | Named business, DWIT, security, network, operations contacts plus Boomi implementation and 24x7 support

## Success Criteria
ID | Criterion
SC1 | Leg A delivers the file into the ADR or Data Lake landing area
SC2 | Leg B delivers directly to ONS and receipt is acknowledged
SC3 | Both legs configured in Dev and promoted through approval-controlled CI/CD
SC4 | Scheduling runs without manual intervention; transfer history visible end to end
SC5 | Non-arrival, transfer failure and scan failure raise evidenced alerts to a named team
SC6 | Each transfer creates an auditable record: source, destination, size, checksum, timestamps, outcome

## Recommendations
ID | Recommendation | Rationale
R1 | Treat connectivity as the critical path | Firewall, allow-list and ONS changes take longest. Raise them in P0/P1 before configuration is ready.
R2 | Test file size against the AV scan ceiling early | If the scan file exceeds the approx 250 MB AV limit (G-15), the scan-failure path becomes the normal path.
R3 | Decide credential storage explicitly | No documented native route to enterprise PAM (G-14). Record the MVP choice and the target state as a decision.
R4 | Document rollback for config promotion | MFT configuration is data, not a build artefact (G-13). Prove rollback as re-promotion of the prior version.
R5 | Build against current ADR, re-point later | Proving re-pointing to the Data Lake as a config-only change is itself evidence for scale.
R6 | Prove SFTP through any load balancer early | Protocol-layer load balancing, source NAT and allow-lists can break external delivery to ONS.
R7 | Keep the legacy route warm until live proof | Run the first production quarter with a fallback to UTM and IF/SDES until SC1 and SC2 are evidenced.
R8 | Agree the ONS acknowledgement mechanism | SC2 requires acknowledged receipt; confirm what counts as an acknowledgement before build.