Boomi Managed File Transfer

MVP | Recommended High-Level Delivery Steps

Companion to the MVP Executive Concept Note (Draft v0.2). Dates are intentionally excluded. Steps are sequenced by dependency and grouped into phases with exit gates, so they can be scheduled once environment and connectivity lead times are known.

# 1. Use case recap

| Item | Detail |
| --- | --- |
| Candidate | ADR.040 / ADR.041 Migrant Workers Scan (quarterly feed) |
| Leg A | NPS to ADR landing area (replaces current UTM transfer) |
| Leg B | ADR output area direct to ONS (removes IF and SDES server hop) |

# 2. Phase overview

| ID | Phase | Track | Exit gate |
| --- | --- | --- | --- |
| P0 | Mobilise and confirm | Governance | Decision log signed off; owners named; file profile confirmed |
| P1 | Environments and connectivity | Platform (critical path) | All endpoints reachable from runtime in lower environments with evidence |
| P2 | Security and credentials | Security | Security design approved; credentials and keys in place |
| P3 | Configure Leg A (NPS to ADR) | Build | Leg A runs in Dev with a synthetic file |
| P4 | Configure Leg B (ADR to ONS) | Build | Leg B delivers to ONS lower environment with acknowledgement |
| P5 | CI/CD promotion | Build | Both legs promoted to Pre-prod via approved pipeline with audit trail |
| P6 | Observability and audit | Operate | Dashboards and alerts demonstrated to operations |
| P7 | Test | Assure | Evidence pack reviewed; defects closed or accepted |
| P8 | Prove in production and hand over | Operate | Live feed delivered; service accepted by operations |
| P9 | Go/no-go and scale recommendation | Governance | Recommendation issued; definition of done met |

# 3. Sequencing

- Start together: P0 and P1 (network and ONS agreement are the longest lead items)

- Then in parallel: P2 security, P3 Leg A, P4 Leg B

- Once legs run in Dev: P5 CI/CD and P6 observability

- Sequential close: P7 test, P8 production and handover, P9 recommendation

# 4. Steps by phase

## P0 Mobilise and confirm

Lock the decisions and people the MVP depends on before any build starts.

- Confirm ADR.040/041 as the MVP candidate and record the executive decision

- Name owners for business, DWIT, security, network, operations, Boomi implementation and 24x7 support

- Confirm data classification, file naming rules, typical and peak file sizes, and quarterly schedule

- Record decision D7: build against current ADR endpoints, re-point to Data Lake later as a configuration change

- Open a RAID log and decision log with named owners; agree go/no-go criteria up front (use SC1 to SC6)

Dependencies: D5, D7, D8   |   Success criteria: -   |   Lead role: MVP Lead / Service Owner

Exit gate: Decision log signed off; owners named; file profile confirmed

## P1 Environments and connectivity

Raise the long-lead infrastructure and network changes on day one.

- Confirm Dev, Test, Pre-prod and Prod MFT tenants and MFT CI/CD portal access

- Install and register organisation-hosted runtimes; confirm Windows Server hardening and Defender AV (D6)

- Raise firewall and allow-list changes for NPS, ADR and ONS in every environment (inbound and outbound, protocol and port)

- Agree with ONS the new sending endpoint, source IPs and a production-like lower environment

- Run a connectivity smoke test per endpoint per environment (TCP, protocol handshake, auth) and record evidence

Dependencies: D1, D2, D3, D4, D6   |   Success criteria: -   |   Lead role: Platform Engineer / Network

Exit gate: All endpoints reachable from runtime in lower environments with evidence

## P2 Security and credentials

Make the secure-transfer controls explicit rather than assumed.

- Exchange SSH host keys / certificates and pin them; agree key rotation ownership

- Decide credential storage: native MFT vault now, or documented route to enterprise PAM (tracked gap G-14)

- Confirm AV scanning point and behaviour on scan failure (quarantine, alert, no onward delivery)

- Check feed file size against AV scan ceiling (about 250 MB, gap G-15); design split or exception if exceeded

- Obtain security sign-off of the transfer design for the confirmed classification

Dependencies: D2, D3, D5, D6   |   Success criteria: SC5, SC6   |   Lead role: Security Architect

Exit gate: Security design approved; credentials and keys in place

## P3 Configure Leg A (NPS to ADR)

Configure, not construct: one transfer definition per leg driven by configuration.

- Define source and target endpoints, file mask and naming rules

- Set schedule and non-arrival window aligned to the quarterly feed

- Configure AV scan, archive, quarantine, retry and checksum validation

- Configure alerts for non-arrival, transfer failure and scan failure to a named team

- Parameterise environment-specific values so promotion changes config, not design

Dependencies: D1, D3, D5   |   Success criteria: SC1, SC4, SC5, SC6   |   Lead role: Boomi MFT Engineer

Exit gate: Leg A runs in Dev with a synthetic file

## P4 Configure Leg B (ADR to ONS)

Replace the IF and SDES hop with a direct, audited external delivery.

- Define ADR output source and ONS external target with pinned host key / certificate

- Set trigger (schedule or event after Leg A processing chain completes)

- Configure AV scan, archive, quarantine, retry and checksum validation

- Agree and configure the ONS receipt acknowledgement method

- Configure alerts and audit record fields as per SC6

Dependencies: D3, D4, D5   |   Success criteria: SC2, SC4, SC5, SC6   |   Lead role: Boomi MFT Engineer

Exit gate: Leg B delivers to ONS lower environment with acknowledgement

## P5 CI/CD promotion

Prove repeatable, approval-controlled promotion across environments.

- Package both leg configurations in the MFT CI/CD portal

- Define approval roles (requester, approver) and segregation of duties

- Promote Dev to Test to Pre-prod with environment overrides only

- Test and document rollback: config rows are data, so rollback is a re-promotion of the prior version (gap G-13)

- Capture promotion audit evidence for each step

Dependencies: D1   |   Success criteria: SC3   |   Lead role: Platform Engineer

Exit gate: Both legs promoted to Pre-prod via approved pipeline with audit trail

## P6 Observability and audit

Treat visibility as a feature from the first run.

- Confirm transfer history view covers both legs end to end

- Verify audit record fields: source, destination, file size, checksum, timestamps, outcome

- Route alerts to the named team; ServiceNow or Dynatrace only if essential for readiness

- Define simple service KPIs: on-time delivery, failures, mean time to recover

Dependencies: D8   |   Success criteria: SC4, SC5, SC6   |   Lead role: Operations Lead

Exit gate: Dashboards and alerts demonstrated to operations

## P7 Test

Evidence positive and negative paths in a production-like environment.

- Positive: Leg A and Leg B end to end with representative file sizes

- Negative: non-arrival, target unavailable, credential failure, AV scan failure, checksum mismatch, duplicate file

- Recovery: retry, re-run from archive, release from quarantine

- Promotion and rollback test via CI/CD portal

- Collate a test evidence pack mapped to SC1 to SC6

Dependencies: D4, D5   |   Success criteria: SC1, SC2, SC3, SC4, SC5, SC6   |   Lead role: Test Lead

Exit gate: Evidence pack reviewed; defects closed or accepted

## P8 Prove in production and hand over

Run the live feed and transfer ownership to the service.

- Promote to Prod through CI/CD with change approval

- Run the live quarterly transfer with hypercare and parallel check against the legacy route

- Decommission or disable the UTM and IF/SDES route once delivery is confirmed

- Hand over runbook, alert routing, support model and Boomi 24x7 escalation; run a support drill

- Obtain service acceptance from operations

Dependencies: D8   |   Success criteria: SC1, SC2, SC4, SC5, SC6   |   Lead role: Service Owner

Exit gate: Live feed delivered; service accepted by operations

## P9 Go/no-go and scale recommendation

Close the MVP with a documented decision on wider adoption.

- Score each success criterion with evidence

- Record lessons learned, open gaps (G-13, G-14, G-15) and platform constraints

- Define the onboarding pattern and template for the next feeds

- Issue go/no-go and wider adoption recommendation to the executive sponsor

Dependencies: -   |   Success criteria: SC1, SC2, SC3, SC4, SC5, SC6   |   Lead role: MVP Lead

Exit gate: Recommendation issued; definition of done met

# 5. Recommendations and risks

| ID | Recommendation | Rationale |
| --- | --- | --- |
| R1 | Treat connectivity as the critical path | Firewall, allow-list and ONS changes take longest. Raise them in P0/P1 before configuration is ready. |
| R2 | Test file size against the AV scan ceiling early | If the scan file exceeds the approx 250 MB AV limit (G-15), the scan-failure path becomes the normal path. |
| R3 | Decide credential storage explicitly | No documented native route to enterprise PAM (G-14). Record the MVP choice and the target state as a decision. |
| R4 | Document rollback for config promotion | MFT configuration is data, not a build artefact (G-13). Prove rollback as re-promotion of the prior version. |
| R5 | Build against current ADR, re-point later | Proving re-pointing to the Data Lake as a config-only change is itself evidence for scale. |
| R6 | Prove SFTP through any load balancer early | Protocol-layer load balancing, source NAT and allow-lists can break external delivery to ONS. |
| R7 | Keep the legacy route warm until live proof | Run the first production quarter with a fallback to UTM and IF/SDES until SC1 and SC2 are evidenced. |
| R8 | Agree the ONS acknowledgement mechanism | SC2 requires acknowledged receipt; confirm what counts as an acknowledgement before build. |

# 6. Traceability: dependencies

| ID | Dependency | Needed by |
| --- | --- | --- |
| D1 | Dev, Test, Pre-prod and Prod environments on Boomi SaaS MFT, including MFT CI/CD portal | P1, P3, P5 |
| D2 | Organisation-hosted Boomi runtimes with anti-virus capability | P1, P2 |
| D3 | End-to-end connectivity, firewall and allow-list changes for NPS, ADR/Data Lake and ONS, with credentials, certificates and host keys | P1, P2, P3, P4 |
| D4 | ONS agreement to receive from the new sending endpoint, plus a production-like lower environment | P1, P4, P7 |
| D5 | Representative or synthetic test files, confirmed file naming rules and data classification | P0, P2, P3, P4, P7 |
| D6 | Windows Server readiness including Microsoft Defender Antivirus and platform security controls | P1, P2 |
| D7 | Decision on ADR-to-Data Lake migration (recommended: build against available endpoint, re-point by configuration) | P0 |
| D8 | Named business, DWIT, security, network, operations contacts plus Boomi implementation and 24x7 support | P0, P6, P8 |

# 7. Traceability: success criteria

| ID | Success criterion | Evidenced in |
| --- | --- | --- |
| SC1 | Leg A delivers the file into the ADR or Data Lake landing area | P3, P7, P8, P9 |
| SC2 | Leg B delivers directly to ONS and receipt is acknowledged | P4, P7, P8, P9 |
| SC3 | Both legs configured in Dev and promoted through approval-controlled CI/CD | P5, P7, P9 |
| SC4 | Scheduling runs without manual intervention; transfer history visible end to end | P3, P4, P6, P7, P8, P9 |
| SC5 | Non-arrival, transfer failure and scan failure raise evidenced alerts to a named team | P2, P3, P4, P6, P7, P8, P9 |
| SC6 | Each transfer creates an auditable record: source, destination, size, checksum, timestamps, outcome | P2, P3, P4, P6, P7, P8, P9 |