## Backlog
HMRC — MFT on Boomi · 8-Week Delivery Backlog
4 × 2-week sprints · Discovery to first MFT interface live in Development · includes Intelligrator user stories
ID | Sprint | Workstream | Persona | User story title | Priority (MoSCoW) | Points | Acceptance criteria
S1-01 | Sprint 1 | Programme | Delivery Lead | Team onboarding & ways of working | Must | 3 | Squad, roles and RACI published • Ceremony cadence and Definition of Done agreed • Backlog tool and boards set up
S1-02 | Sprint 1 | MFT Interface | Platform Engineer | Boomi Dev environment & MFT access | Must | 5 | Boomi accounts provisioned with correct roles • Dev Atom/Molecule runtime available • MFT capability enabled and reachable
S1-03 | Sprint 1 | MFT Interface | Integration Architect | Current-state file-transfer discovery | Must | 8 | Inventory captures source/target, protocol, schedule, volume, format, encryption • Interfaces classified by complexity and risk • Inventory reviewed with stakeholders
S1-04 | Sprint 1 | MFT Interface | Product Owner | Pilot interface selection | Must | 3 | Scoring criteria agreed (risk, value, complexity) • Shortlist scored • Pilot selected and signed off
S1-05 | Sprint 1 | MFT Interface | Integration Architect | MFT operating model & guardrails | Should | 5 | Postal model (Organizations/Flows/Endpoints) usage defined • AFT vs File Sharing selection criteria documented • Naming, channels and monitoring conventions agreed
S1-06 | Sprint 1 | Intelligrator | Product Owner | Intelligrator vision & MVP scope | Must | 3 | MVP boundary agreed (in/out of scope) • Personas confirmed • Success measures defined
S1-07 | Sprint 1 | Intelligrator | MFT Admin | Persona & permission model | Should | 3 | Personas mapped to permissions • Least-privilege model documented • Segregation of duties preserved (requester ≠ approver)
S2-01 | Sprint 2 | MFT Interface | Integration Architect | Pilot interface solution design | Must | 8 | SDD covers full transfer path and endpoints • Protocol, schedule and error handling specified • Design reviewed and signed off
S2-02 | Sprint 2 | MFT Interface | Platform Engineer | Connectivity & network readiness | Must | 5 | Firewall/route requests raised and confirmed • SFTP host keys exchanged • Connectivity verified from Dev runtime
S2-03 | Sprint 2 | MFT Interface | Security Architect | Security & key-management design | Must | 5 | PGP key lifecycle defined • Credential vaulting approach agreed • Data-classification handling documented
S2-04 | Sprint 2 | MFT Interface | Integration Architect | Config-driven engine design | Must | 8 | Config schema defines one row per interface • Generic engine behaviour specified • No per-request component generation required
S2-05 | Sprint 2 | MFT Interface | Operations Analyst | Monitoring & alerting design | Should | 5 | Monitoring approach mapped to Activity Page • Alert thresholds and channels defined • SLA targets agreed
S2-06 | Sprint 2 | Intelligrator | Platform Engineer | Intelligrator data model & config schema | Must | 5 | Data model covers request, approval and interface entities • Request fields map to engine config columns • Schema reviewed
S2-07 | Sprint 2 | Intelligrator | Requester | Wizard field specification | Must | 5 | All mandatory provisioning fields captured • Validation rules defined • Wizard steps and help text specified
S2-08 | Sprint 2 | Intelligrator | Approver | Approval queue & lifecycle design | Must | 5 | State machine documented with allowed transitions • Approval queue behaviour defined • Rejection and rework paths covered
S3-01 | Sprint 3 | MFT Interface | Platform Engineer | Configure pilot Organizations/Flow/Endpoints | Must | 8 | Organizations and Flow created • Source and target Endpoints configured • Path validated in Dev
S3-02 | Sprint 3 | MFT Interface | Platform Engineer | Build generic MFT engine process | Must | 8 | Engine reads interface config at runtime • Pilot config row drives the transfer • No hard-coded, per-request logic
S3-03 | Sprint 3 | MFT Interface | Operations Analyst | Error handling, retries & notifications | Must | 5 | Retry policy implemented • Failed files routed to dead-letter handling • Notifications raised on failure
S3-04 | Sprint 3 | MFT Interface | Operations Analyst | Monitoring & alerting build | Should | 3 | Transfers visible on the Activity Page • Alerts fire on failure/SLA breach • Status verified during unit test
S3-05 | Sprint 3 | MFT Interface | Platform Engineer | Unit-test the pilot interface | Must | 3 | Test cases cover happy and error paths • Results recorded • Defects logged and triaged
S3-06 | Sprint 3 | Intelligrator | Requester | Wizard workflow build (MVP) | Must | 8 | Wizard captures and validates all fields • Submission creates a request in Requested state • Request appears in the approval queue
S3-07 | Sprint 3 | Intelligrator | Approver | Approval queue build (MVP) | Must | 5 | Queue lists pending requests with detail • Approve/reject with comments supported • State updates on decision
S3-08 | Sprint 3 | Intelligrator | Platform Engineer | Config-write provisioning trigger | Must | 8 | Approval writes a config row • Generic engine picks up the new interface • No per-request component is generated
S4-01 | Sprint 4 | MFT Interface | Test Analyst | End-to-end SIT | Must | 8 | Positive and negative cases pass • Encryption and large-file cases pass • Resend/reprocess verified; results recorded
S4-02 | Sprint 4 | MFT Interface | Platform Engineer | Deploy interface to Development | Must | 5 | Interface deployed to Dev • Scheduled transfer runs successfully • Deployment recorded/repeatable
S4-03 | Sprint 4 | MFT Interface | Operations Analyst | Operational runbook & support model | Should | 3 | Runbook covers operate, monitor and recover • Escalation path defined • Reviewed with support
S4-04 | Sprint 4 | Intelligrator | Requester | Lifecycle transitions & status visibility | Should | 5 | State shown to requester • Transitions reflect real provisioning status • Active state confirmed on go-live
S4-05 | Sprint 4 | Intelligrator | Auditor | Audit log | Must | 3 | Request, approval and provisioning events logged • Actor and timestamp captured • Log is tamper-evident/immutable
S4-06 | Sprint 4 | Intelligrator | Product Owner | Provision-into-Dev demo (end-to-end) | Must | 5 | Full flow demonstrated end-to-end • Interface active in Dev after approval • Stakeholder sign-off captured
S4-07 | Sprint 4 | Programme | Delivery Lead | Go/No-go & Phase-2 backlog | Must | 3 | Go/no-go decision recorded • Retro actions captured • Phase-2 backlog prioritised
TOTAL |  |  |  |  | 30 stories | 156

## Sprint plan
Sprint plan — goals, activities, deliverables & milestones
Sprint | Weeks / Phase | Sprint goal | Key activities | Deliverables & milestone
Sprint 1 | Weeks 1–2 Discovery & Mobilisation | Stand up the squad and access, understand the current-state file-transfer landscape, agree the pilot interface, and establish the target MFT operating model on Boomi. Confirm Intelligrator MVP scope and personas. | • Team onboarding, RACI, ways of working and ceremony cadence agreed • Environment access requested: Boomi platform, Dev runtime (Atom/Molecule) and native MFT capability enablement • Current-state discovery: inventory of existing file interfaces (endpoints, protocols, schedules, volumes, file formats, encryption) • Pilot interface scored, shortlisted and selected • Target MFT operating model documented — Thru-based postal model (Organizations / Flows / Endpoints), Automated File Transfer vs File Sharing, Management vs Data channels, naming and Activity-Page monitoring conventions • Intelligrator vision, MVP boundary and personas (Requester, MFT Admin/Approver, Platform Engineer, Auditor) confirmed | • Current-state file-transfer inventory • Pilot interface selection & scoring • Mobilisation pack & RACI • MFT operating model v0.1 • Intelligrator MVP scope statement ★ M1 — Discovery complete, pilot selected, Dev + MFT access secured.
Sprint 2 | Weeks 3–4 Solution Design & Environment Readiness | Produce the detailed design for the pilot MFT interface, provision and secure the Dev environment and connectivity, and design the Intelligrator config-driven provisioning model, wizard, approval queue and lifecycle. | • Pilot interface solution design (SDD): Organizations, Flow, source/target Endpoints, protocol (SFTP/AS2), schedule, transformation (if any), error handling • Connectivity & network readiness: firewall rules, routes, SFTP host keys, IP allow-listing in Dev • Security & key-management design: PGP handling, credential vaulting, data-classification controls in transit and at rest • Config-driven engine design: single generic MFT engine process driven by a config table (one row per interface) — preferred over per-request component generation • Monitoring & alerting design against the Activity Page, with alert thresholds and SLAs • Intelligrator: data model, provisioning config schema, wizard field spec, approval queue design and lifecycle state machine | • Pilot interface Solution Design Document (SDD) • Environment & connectivity readiness checklist • Config/cross-reference schema & data model • Intelligrator design pack (wizard + approval + states) ★ M2 — Solution design signed off; environment & connectivity ready.
Sprint 3 | Weeks 5–6 Build & Configure | Build and configure the pilot MFT interface using the config-driven engine, and build the Intelligrator MVP (wizard → approval → provisioning trigger). | • Configure Boomi MFT Organizations, Flow and source/target Endpoints for the pilot • Build the generic MFT engine process, parameterised from the config table • Populate the config/cross-reference row for the pilot interface • Implement error handling, retries, dead-letter handling, notifications and logging • Wire up monitoring & alerting via the Activity Page in Dev • Intelligrator MVP: wizard workflow, approval queue, config-write on approval and provisioning trigger into the generic engine • Unit-test the configured components | • Configured, unit-tested pilot MFT interface • Generic MFT engine process • Intelligrator MVP build (wizard + approval + provisioning trigger) • Unit-test evidence ★ M3 — Pilot built & unit-tested; Intelligrator MVP built.
Sprint 4 | Weeks 7–8 Test, Deploy to Dev & Handover | End-to-end SIT of the pilot interface, deploy to Development, produce the runbook, and demonstrate Intelligrator provisioning into Dev end-to-end. Decide Dev go/no-go and shape the Phase-2 backlog. | • End-to-end SIT: automated file transfer source → Boomi MFT → target; positive, negative, encryption, large-file and resend cases • Non-functional checks: throughput, file size, schedule adherence • Deploy the pilot interface to Development (config row / packaged component) • Operational runbook & support model (start/stop, reprocessing, alerts, escalation) • Intelligrator: lifecycle transitions (Requested → Approved → Provisioned → Active → Retired), audit log, and provisioning-into-Dev demonstrated • Sprint review & Dev go/no-go; retrospective; prioritised Phase-2 backlog | • SIT results & defect log • Pilot MFT interface live in Development • Operational runbook • Intelligrator end-to-end provisioning demo + audit trail • Phase-2 backlog & recommendations ★ M4 — MFT interface LIVE in Dev; auto-provisioning demonstrated.

## Summary
Points by sprint & workstream
Sprint | MFT Interface | Intelligrator | Programme | Total pts | Stories
Sprint 1 | 21 | 6 | 3 | 30 | 7
Sprint 2 | 31 | 15 | 0 | 46 | 8
Sprint 3 | 27 | 21 | 0 | 48 | 8
Sprint 4 | 16 | 13 | 3 | 32 | 7
Total | 95 | 55 | 6 | 156 | 30

## WoW & RAID
Ways of working
Ceremony | When | Who | Purpose
Sprint Planning | Day 1 of each sprint | Team + PO | Commit sprint goal and backlog for the two weeks.
Daily Stand-up | Daily, 15 min | Delivery team | Progress, plan, blockers.
Backlog Refinement | Mid-sprint | Team + PO | Groom and estimate upcoming stories; keep two-sprints-ahead ready.
Sprint Review | Last day | Team + stakeholders | Demo increment; gather feedback; confirm milestone.
Retrospective | Last day | Delivery team | Inspect and adapt ways of working.
Definition of Ready
• Story has a clear user-value statement and acceptance criteria
• Dependencies and test data identified
• Sized by the team and small enough for one sprint
• No unresolved blocking questions
Definition of Done
• Acceptance criteria met and demonstrated
• Built config-driven (no per-request components) where applicable
• Unit-tested; defects logged/triaged
• Peer-reviewed and documented
• Deployed to the target environment for the sprint
• Published web page uses generic programme terms only (governance naming rule)
RAID
Type | Description | Impact | Mitigation / action
Risk | MFT capability enablement or Dev runtime access slips | Blocks Sprint 1–2 build path | Raise access requests on day 1; track to M1; escalate early.
Assumption | One pilot interface is in scope for the 8 weeks | Keeps scope achievable to Dev deployment | Confirm at pilot selection (S1-04).
Issue | Source/target endpoint owners unavailable for connectivity | Delays SIT | Book connectivity slots in Sprint 2; confirm host keys early.
Dependency | Firewall/network changes for SFTP endpoints | Gates connectivity and SIT | Raise in Sprint 2; verify from Dev runtime before build.
Dependency | Security sign-off on PGP/credential handling | Gates go-live in Dev | Design in Sprint 2; sign off before Sprint 4 deploy.