## Summary
MFT on Boomi (Thru) — Capability & Gap Register
OFFICIAL — companion to the Solution Design Document v0.1 (20 Jul 2026)
Capabilities by maturity | Count
GA / relied-upon | 15
Available - confirm fit | 6
Roadmap / validate | 1
Total capabilities | 23
Gaps by severity | Count
High | 3
Medium | 10
Low | 2
Total gaps | 15
How to use this register
• Capability Register — what Boomi native MFT provides and how each item is used in the estate. Maturity: GA = relied upon; Confirm = available, validate fit; Roadmap = validate at build.
• Gap Register — limitations with impact, severity, and the mitigation/action each drives. Assign a named Owner and move Status from Open before build.
• High-severity gaps (data residency/assurance, audit retention, and MFT credential/PAM sourcing) most affect go-live for OFFICIAL data. The missing native CI/CD pipeline (G-13) is the main delivery/operability drawback.
• This register is the single source for the SDD Section 9 matrix and Section 11 gaps — keep them in step.

## Capability Register
Ref | Capability | Description | How used in the HMRC estate | Maturity | Source
C-01 | SFTP / FTPS / AS2 endpoints | Secure protocol endpoints under Organizations > Endpoints > Flows; MFT SFTP on port 22 | Inbound/outbound with OGDs, agents, banks | GA | Boomi MFT docs
C-02 | Trading-partner onboarding | Partner/community model; unified trading-partner framework extending to MFT | Config-driven partner & endpoint records | Confirm | Boomi roadmap Q2-2026
C-03 | Event-driven trigger | File arrival triggers a Boomi Integration process via MFT Connector | Kicks off the generic engine / processing | GA | Thru / Boomi
C-04 | Persistence & guaranteed delivery | File persistence with automatic retry and fault tolerance | Resilient delivery to systems of record | GA | Boomi 'What is MFT'
C-05 | PGP encryption (incl. ASCII-armor) | Encrypt/decrypt payloads; .asc armor format | At-rest protection of OFFICIAL payloads | GA | Mar-2026 release
C-06 | TAR archive / extract | Archive/extract TAR (optional compression) in Flow Endpoints | Bundle/unbundle batch file sets | GA | Mar-2026 release
C-07 | Tracking & audit log | End-to-end visibility with delivery confirmation; single source of truth | Central audit of all transfers | GA | Boomi MFT product
C-08 | Scheduling & polling | Time-based automated file transfer with schedule history | Batch windows and source polling | GA | Boomi MFT product
C-09 | OpenTelemetry observability | Export metrics, logs, traces to external monitoring via Runtime Mgmt UI | Feed enterprise SIEM (Splunk) | Confirm | Boomi roadmap Q2-2026
C-10 | Runtime health/heartbeat telemetry | Improved heartbeat telemetry for runtime status/diagnostics | Proactive ops monitoring/alerting | GA | Mar-2026 release
C-11 | Hybrid runtime (on-prem + cloud) | MFT cloud components + on-prem MFT runtimes + MFT Connector in processes | Keep OFFICIAL payload in boundary | Confirm | Boomi roadmap Q2-2026
C-12 | DSA legacy SFTP host keys | Continued support for deprecated DSA host keys | Serve legacy external SFTP partners | GA (legacy) | Mar-2026 release
C-13 | Automated data retention | Auto cleanup: schedule history 3mo, audit logs 12mo | Housekeeping (see gap G-02b) | GA | Mar-2026 release
C-14 | PEPPOL via Boomi EDI VAN | Native PEPPOL support path for e-procurement compliance | Only if PEPPOL flows required | Roadmap | Boomi roadmap Q2-2026
C-15 | Extensive APIs | Full functionality via APIs across all tiers | Automation of onboarding/ops | GA | Thru datasheet
C-16 | Secrets Management Service | Binds Integration runtime to cloud vaults (e.g. Azure Key Vault) for connector credentials; Nov-2025 release | Runtime credentials — NOT confirmed for MFT endpoint/partner creds (see G-14) | Confirm | Boomi community Nov-2025
C-17 | CI/CD via AtomSphere API + DevOps | Reference framework to promote Boomi assets through external DevOps tooling; not MFT-config-aware | Config promotion must be built externally (see G-13) | Confirm | Boomi DevOps guide
C-18 | Integration Platform interoperability | Boomi MFT Connector lets an integration process invoke MFT file-transfer flows (event-driven orchestration; control vs data channels) | MFT triggered/orchestrated by integration flows; one platform & audit trail | GA | Boomi MFT connector docs
C-19 | API Management fronting MFT/integration APIs | CAM + external/internal API gateways (and Kong) publish and secure MFT/integration APIs to consumers and HoD apps | Governed API access instead of point-to-point | Confirm | Boomi CAM docs
C-20 | Antivirus / malware scanning | Real-time AV scan of files in flight; infected files auto-quarantined; built into every layer (zero-trust, SOC 2) | Malware blocked before delivery; defence in depth | GA | Boomi MFT security
C-21 | Automated File Transfer (AFT) | Scheduled/event-driven system-to-system transfers; many-to-many endpoints; retry, auto-resume, exception handling, notifications | Unattended, guaranteed delivery; config-driven | GA | Boomi MFT / Thru
C-22 | Ad-hoc file sharing (EFSS) | Person-to-person secure large-file sharing; web UI, Outlook/Salesforce/SharePoint plugins, drop-box inbound; per-user/group permissions | Governed user file sharing under same controls | Confirm scope | Boomi MFT / Thru
C-23 | File-level (end-to-end) encryption | File encrypted at file level in addition to protocol-in-transit and at-rest storage encryption | Stronger data protection for OFFICIAL | GA | Boomi MFT platform

## Gap Register
Ref | Gap / limitation | Impact | Severity | Mitigation / action | Owner | Status
G-01 | Native MFT post-acquisition (May-2025), still maturing; roadmap items in flight | Feature-parity / roadmap risk | Medium | Confirm live GA feature set at build; track roadmap; don't design on roadmap-only items | TBC | Open
G-02a | Control plane is SaaS; data residency/assurance for OFFICIAL to confirm | Assurance / compliance risk | High | Confirm UK region; keep payload on-prem via hybrid runtime; assurance review | TBC | Open
G-02b | Automated audit retention default 12 months (schedule history 3 months) | May breach statutory retention | High | Export audit to long-term archive; set retention policy | TBC | Open
G-03 | Native protocols centre on SFTP/FTPS/AS2 (+PEPPOL via EDI VAN); OFTP2/AS4/PeSIT not native | Gap if partners mandate these | Medium | Survey partner protocols; bridge/third-party gateway where required | TBC | Open
G-04 | Content-based routing/transform beyond filename needs Integration processes | 'Construction' creep vs principle | Medium | Keep logic in shared engine; DA deviation with named owner | TBC | Open
G-05 | Batch throughput vs WebMethods unproven for HMRC volumes | Performance risk at cutover | Medium | Benchmark peak batch before migrating high-volume flows | TBC | Open
G-06 | Working-day/holiday-calendar scheduling depth to confirm | Complex windows may need external scheduler | Low | Validate scheduling; integrate enterprise scheduler if needed | TBC | Open
G-07 | Non-repudiation/signed-receipt depth vs dedicated MFT to confirm | Compliance evidence risk | Medium | Confirm receipt/NR capability against requirements | TBC | Open
G-08 | MFT gateway HA topology (vs Atom HA) to confirm | Availability risk at edge | Medium | Confirm supported gateway clustering with vendor | TBC | Open
G-09 | Enterprise HSM/KMS integration for keys to confirm | Key-custody assurance | Medium | Confirm HSM/KMS integration pattern | TBC | Open
G-10 | SIEM integration relies on OpenTelemetry export - confirm coverage | Monitoring completeness | Low | Prove OTel -> Splunk coverage of MFT events | TBC | Open
G-12 | No automated WebMethods -> Boomi migration tooling | Migration effort / time | Medium | Deliberate re-configuration; sequence by risk | TBC | Open
G-13 | No native CI/CD pipeline for MFT config; promotion dev->test->prod is UI/admin-driven and environment-promotion not fully API-automatable | Manual promotion; weak traceability, review, rollback | Medium | Build external CI/CD over AtomSphere APIs + DevOps tooling; hold config/routing table in Git; gated audited promotion | TBC | Open
G-14 | No documented native path to source MFT endpoint/partner credentials from enterprise password/secrets manager (e.g. CyberArk PAM); Secrets Mgmt Service targets Integration runtime + cloud vaults, not MFT partner creds | Credentials in MFT store; weaker central rotation & PAM governance | High | Validate MFT credential sourcing with vendor; broker via Integration + secrets service or controlled vault sync; agree with Security | TBC | Open
G-15 | AV scan applies to files up to ~250 MB on the multi-tenant automated service; larger files need a dedicated single-tenant configuration | Large tax/customs payloads may bypass or exceed native AV scanning | Medium | Confirm max in-scope file size; dedicated/single-tenant config, chunking, or external ICAP/AV for oversize files; agree with Security | TBC | Open